## Slide 1
Refinery Turnaround Schedule
Free Gantt chart template · gantts.app

## Slide 2
Refinery Turnaround Schedule
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Long-range planning
Business case & objectives
Preliminary budget & window
◆ Turnaround sanctioned
Scope development & freeze
Worklist collection
Challenge & risk ranking
◆ Scope frozen
Work package development
Job plans & isolation strategy
Contractor scoping & award
Procurement & long-lead
Long-lead equipment order
Scaffolding & site mobilization
Execution window
Shutdown & cool-down
Isolation & permits
Inspection & discovery
Mechanical repair work
Reassembly & testing
◆ Mechanical completion
Start-up & close-out
Re-commissioning & start-up
◆ Return to service
Demobilization & review
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Long-range planning |  | 2026-08-02 | 2026-09-30 | 60 | 100%
1.1 | Business case & objectives | TA Manager | 2026-08-02 | 2026-08-21 | 20 | 100%
1.2 | Preliminary budget & window | Planning | 2026-08-20 | 2026-09-10 | 22 | 100%
2 | Turnaround sanctioned |  | 2026-10-01 | 2026-10-01 | — | —
3 | Scope development & freeze |  | 2026-10-01 | 2026-11-19 | 50 | 70%
3.1 | Worklist collection | Operations | 2026-10-01 | 2026-10-25 | 25 | 100%
3.2 | Challenge & risk ranking | TA Team | 2026-10-23 | 2026-11-09 | 18 | 60%
4 | Scope frozen |  | 2026-11-20 | 2026-11-20 | — | —
5 | Work package development |  | 2026-11-10 | 2026-12-24 | 45 | 30%
5.1 | Job plans & isolation strategy | Planning | 2026-11-10 | 2026-12-07 | 28 | 40%
5.2 | Contractor scoping & award | Contracts | 2026-11-28 | 2026-12-24 | 27 | 20%
6 | Procurement & long-lead |  | 2026-11-05 | 2027-01-13 | 70 | 25%
6.1 | Long-lead equipment order | Procurement | 2026-11-05 | 2026-12-29 | 55 | 40%
6.2 | Scaffolding & site mobilization | Contractor | 2026-12-30 | 2027-01-13 | 15 | 0%
7 | Execution window |  | 2027-01-14 | 2027-02-06 | 24 | 0%
7.1 | Shutdown & cool-down | Operations | 2027-01-14 | 2027-01-16 | 3 | 0%
7.2 | Isolation & permits | Operations | 2027-01-17 | 2027-01-18 | 2 | 0%
7.3 | Inspection & discovery | Inspection | 2027-01-19 | 2027-01-23 | 5 | 0%
7.4 | Mechanical repair work | Mechanical | 2027-01-23 | 2027-02-01 | 10 | 0%
7.5 | Reassembly & testing | Mechanical | 2027-02-01 | 2027-02-06 | 6 | 0%
8 | Mechanical completion |  | 2027-02-07 | 2027-02-07 | — | —

## Slide 4
9 | Start-up & close-out |  | 2027-02-07 | 2027-02-20 | 14 | 0%
9.1 | Re-commissioning & start-up | Operations | 2027-02-07 | 2027-02-12 | 6 | 0%
10 | Return to service |  | 2027-02-13 | 2027-02-13 | — | —
10.1 | Demobilization & review | TA Team | 2027-02-13 | 2027-02-20 | 8 | 0%