## Gantt
Refinery Turnaround Schedule
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22
1 | Long-range planning |  | 2026-08-02 | 2026-09-30 | 60
1.1 | Business case & objectives | TA Manager | 2026-08-02 | 2026-08-21 | 20
1.2 | Preliminary budget & window | Planning | 2026-08-20 | 2026-09-10 | 22
2 | ◆ Turnaround sanctioned |  | 2026-10-01 | 2026-10-01 | [9 empty] | ◆
3 | Scope development & freeze |  | 2026-10-01 | 2026-11-19 | 50
3.1 | Worklist collection | Operations | 2026-10-01 | 2026-10-25 | 25
3.2 | Challenge & risk ranking | TA Team | 2026-10-23 | 2026-11-09 | 18
4 | ◆ Scope frozen |  | 2026-11-20 | 2026-11-20 | [16 empty] | ◆
5 | Work package development |  | 2026-11-10 | 2026-12-24 | 45
5.1 | Job plans & isolation strategy | Planning | 2026-11-10 | 2026-12-07 | 28
5.2 | Contractor scoping & award | Contracts | 2026-11-28 | 2026-12-24 | 27
6 | Procurement & long-lead |  | 2026-11-05 | 2027-01-13 | 70
6.1 | Long-lead equipment order | Procurement | 2026-11-05 | 2026-12-29 | 55
6.2 | Scaffolding & site mobilization | Contractor | 2026-12-30 | 2027-01-13 | 15
7 | Execution window |  | 2027-01-14 | 2027-02-06 | 24
7.1 | Shutdown & cool-down | Operations | 2027-01-14 | 2027-01-16 | 3
7.2 | Isolation & permits | Operations | 2027-01-17 | 2027-01-18 | 2
7.3 | Inspection & discovery | Inspection | 2027-01-19 | 2027-01-23 | 5
7.4 | Mechanical repair work | Mechanical | 2027-01-23 | 2027-02-01 | 10
7.5 | Reassembly & testing | Mechanical | 2027-02-01 | 2027-02-06 | 6
8 | ◆ Mechanical completion |  | 2027-02-07 | 2027-02-07 | [28 empty] | ◆
9 | Start-up & close-out |  | 2027-02-07 | 2027-02-20 | 14
9.1 | Re-commissioning & start-up | Operations | 2027-02-07 | 2027-02-12 | 6
10 | ◆ Return to service |  | 2027-02-13 | 2027-02-13 | [28 empty] | ◆
10.1 | Demobilization & review | TA Team | 2027-02-13 | 2027-02-20 | 8