## Slide 1
Research / Thesis Plan
Free Gantt chart template · gantts.app

## Slide 2
Research / Thesis Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Proposal
Literature review
Research question & proposal
◆ Proposal approved
Data collection
Design methodology
Fieldwork / experiments
Analysis & Writing
Data analysis
Write chapters
Submission
Revisions & proofread
◆ Submit thesis
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Proposal |  | 2026-08-02 | 2026-08-22 | 21 | 100%
1.1 | Literature review | You | 2026-08-02 | 2026-08-15 | 14 | 100%
1.2 | Research question & proposal | You | 2026-08-16 | 2026-08-22 | 7 | 90%
1.3 | Proposal approved |  | 2026-08-23 | 2026-08-23 | — | —
2 | Data collection |  | 2026-08-23 | 2026-10-01 | 40 | 20%
2.1 | Design methodology | You | 2026-08-23 | 2026-09-01 | 10 | 40%
2.2 | Fieldwork / experiments | You | 2026-09-02 | 2026-10-01 | 30 | 5%
3 | Analysis & Writing |  | 2026-10-02 | 2026-11-15 | 45 | 0%
3.1 | Data analysis | You | 2026-10-02 | 2026-10-21 | 20 | 0%
3.2 | Write chapters | You | 2026-10-16 | 2026-11-14 | 30 | 0%
4 | Submission |  | 2026-11-16 | 2026-11-25 | 10 | 0%
4.1 | Revisions & proofread | You | 2026-11-16 | 2026-11-23 | 8 | 0%
4.2 | Submit thesis |  | 2026-11-26 | 2026-11-26 | — | —