## Slide 1
Restaurant Opening Timeline
Free Gantt chart template · gantts.app

## Slide 2
Restaurant Opening Timeline
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
Concept & lease
Concept & menu direction
Site search & financial model
Lease negotiation
◆ Lease signed
Design & permits
Space & kitchen design
Architectural drawings
Permit submission & review
◆ Building permit issued
Equipment & smallwares
Kitchen equipment order
Hood & fire suppression order
POS, furniture & smallwares
Build-out
Demolition & MEP rough-in
Kitchen infrastructure
Hood & suppression install
Equipment install
Finishes & front of house
Licensing & inspections
Business licence & food permit
Liquor licence application
Health & fire inspections
◆ Certificate of occupancy
Hiring, menu & soft opening
Chef & management hires
Menu costing & testing
Line staff hiring
Staff training
Friends & family service
Soft opening
◆ Grand opening
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Concept & lease |  | 2026-08-02 | 2026-10-10 | 70 | 100%
1.1 | Concept & menu direction | Owner | 2026-08-02 | 2026-08-31 | 30 | 100%
1.2 | Site search & financial model | Owner | 2026-08-12 | 2026-09-20 | 40 | 100%
1.3 | Lease negotiation | Owner | 2026-09-16 | 2026-10-10 | 25 | 100%
2 | Lease signed |  | 2026-10-11 | 2026-10-11 | — | —
3 | Design & permits |  | 2026-10-11 | 2027-01-08 | 90 | 80%
3.1 | Space & kitchen design | Designer | 2026-10-11 | 2026-11-14 | 35 | 100%
3.2 | Architectural drawings | Architect | 2026-11-05 | 2026-12-04 | 30 | 90%
3.3 | Permit submission & review | Architect | 2026-12-05 | 2027-01-08 | 35 | 50%
4 | Building permit issued |  | 2027-01-09 | 2027-01-09 | — | —
5 | Equipment & smallwares |  | 2026-11-20 | 2027-03-09 | 110 | 30%
5.1 | Kitchen equipment order | Owner | 2026-11-20 | 2027-02-02 | 75 | 40%
5.2 | Hood & fire suppression order | Owner | 2026-11-25 | 2027-02-02 | 70 | 40%
5.3 | POS, furniture & smallwares | Manager | 2027-01-09 | 2027-03-09 | 60 | 10%
6 | Build-out |  | 2027-01-09 | 2027-04-18 | 100 | 0%
6.1 | Demolition & MEP rough-in | GC | 2027-01-09 | 2027-02-12 | 35 | 0%
6.2 | Kitchen infrastructure | GC | 2027-02-08 | 2027-03-09 | 30 | 0%
6.3 | Hood & suppression install | Specialist | 2027-02-23 | 2027-03-14 | 20 | 0%
6.4 | Equipment install | Specialist | 2027-03-10 | 2027-03-29 | 20 | 0%
6.5 | Finishes & front of house | GC | 2027-03-05 | 2027-04-18 | 45 | 0%
7 | Licensing & inspections |  | 2026-10-16 | 2027-05-03 | 200 | 30%

## Slide 4
7.1 | Business licence & food permit | Owner | 2026-10-16 | 2026-11-29 | 45 | 100%
7.2 | Liquor licence application | Owner | 2026-10-16 | 2027-04-03 | 170 | 40%
7.3 | Health & fire inspections | Inspector | 2027-04-09 | 2027-04-28 | 20 | 0%
8 | Certificate of occupancy |  | 2027-05-01 | 2027-05-01 | — | —
9 | Hiring, menu & soft opening |  | 2027-01-29 | 2027-05-13 | 105 | 0%
9.1 | Chef & management hires | Owner | 2027-01-29 | 2027-03-09 | 40 | 20%
9.2 | Menu costing & testing | Chef | 2027-03-05 | 2027-04-08 | 35 | 0%
9.3 | Line staff hiring | Manager | 2027-03-25 | 2027-04-18 | 25 | 0%
9.4 | Staff training | Manager | 2027-04-17 | 2027-05-06 | 20 | 0%
9.5 | Friends & family service | All | 2027-05-04 | 2027-05-07 | 4 | 0%
9.6 | Soft opening | All | 2027-05-08 | 2027-05-13 | 6 | 0%
10 | Grand opening |  | 2027-05-14 | 2027-05-14 | — | —