## Gantt
Restaurant Opening Timeline
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17
1 | Concept & lease |  | 2026-08-02 | 2026-10-10 | 70
1.1 | Concept & menu direction | Owner | 2026-08-02 | 2026-08-31 | 30
1.2 | Site search & financial model | Owner | 2026-08-12 | 2026-09-20 | 40
1.3 | Lease negotiation | Owner | 2026-09-16 | 2026-10-10 | 25
2 | ◆ Lease signed |  | 2026-10-11 | 2026-10-11 | [11 empty] | ◆
3 | Design & permits |  | 2026-10-11 | 2027-01-08 | 90
3.1 | Space & kitchen design | Designer | 2026-10-11 | 2026-11-14 | 35
3.2 | Architectural drawings | Architect | 2026-11-05 | 2026-12-04 | 30
3.3 | Permit submission & review | Architect | 2026-12-05 | 2027-01-08 | 35
4 | ◆ Building permit issued |  | 2027-01-09 | 2027-01-09 | [23 empty] | ◆
5 | Equipment & smallwares |  | 2026-11-20 | 2027-03-09 | 110
5.1 | Kitchen equipment order | Owner | 2026-11-20 | 2027-02-02 | 75
5.2 | Hood & fire suppression order | Owner | 2026-11-25 | 2027-02-02 | 70
5.3 | POS, furniture & smallwares | Manager | 2027-01-09 | 2027-03-09 | 60
6 | Build-out |  | 2027-01-09 | 2027-04-18 | 100
6.1 | Demolition & MEP rough-in | GC | 2027-01-09 | 2027-02-12 | 35
6.2 | Kitchen infrastructure | GC | 2027-02-08 | 2027-03-09 | 30
6.3 | Hood & suppression install | Specialist | 2027-02-23 | 2027-03-14 | 20
6.4 | Equipment install | Specialist | 2027-03-10 | 2027-03-29 | 20
6.5 | Finishes & front of house | GC | 2027-03-05 | 2027-04-18 | 45
7 | Licensing & inspections |  | 2026-10-16 | 2027-05-03 | 200
7.1 | Business licence & food permit | Owner | 2026-10-16 | 2026-11-29 | 45
7.2 | Liquor licence application | Owner | 2026-10-16 | 2027-04-03 | 170
7.3 | Health & fire inspections | Inspector | 2027-04-09 | 2027-04-28 | 20
8 | ◆ Certificate of occupancy |  | 2027-05-01 | 2027-05-01 | [39 empty] | ◆
9 | Hiring, menu & soft opening |  | 2027-01-29 | 2027-05-13 | 105
9.1 | Chef & management hires | Owner | 2027-01-29 | 2027-03-09 | 40
9.2 | Menu costing & testing | Chef | 2027-03-05 | 2027-04-08 | 35
9.3 | Line staff hiring | Manager | 2027-03-25 | 2027-04-18 | 25
9.4 | Staff training | Manager | 2027-04-17 | 2027-05-06 | 20
9.5 | Friends & family service | All | 2027-05-04 | 2027-05-07 | 4
9.6 | Soft opening | All | 2027-05-08 | 2027-05-13 | 6
10 | ◆ Grand opening |  | 2027-05-14 | 2027-05-14 | [41 empty] | ◆