## Slide 1
Retail Store Opening Timeline
Free Gantt chart template · gantts.app

## Slide 2
Retail Store Opening Timeline
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Site & lease
Catchment & footfall analysis
Site shortlist & sales forecast
Lease negotiation
◆ Lease signed
Design & approvals
Store layout to brand standard
Shopfront & signage design
Landlord & centre approval
Building & signage permits
◆ Approvals granted
Fit-out
◆ Landlord handover of unit
Shopfitting & partitions
Flooring & lighting
Fixtures & shelving install
Shopfront & signage install
Snagging
Licensing, systems & loss prevention
Trading licence & registrations
POS & payment terminals
Network & CCTV install
Security tagging & loss prevention
Fire & accessibility inspection
◆ Cleared to trade
Inventory & merchandising
◆ Opening order placed
Supplier lead time & production
Stock delivery & back-of-house set-up
Planogram build
Visual merchandising install
Hiring, training & launch
Store manager hired
Floor team recruitment
Product & POS training
Local marketing & launch comms
Soft launch trading days
◆ Grand opening
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Site & lease |  | 2026-08-02 | 2026-10-05 | 65 | 100%
1.1 | Catchment & footfall analysis | Property | 2026-08-02 | 2026-08-26 | 25 | 100%
1.2 | Site shortlist & sales forecast | Property | 2026-08-20 | 2026-09-13 | 25 | 100%
1.3 | Lease negotiation | Legal | 2026-09-11 | 2026-10-05 | 25 | 100%
2 | Lease signed |  | 2026-10-06 | 2026-10-06 | — | —
3 | Design & approvals |  | 2026-10-06 | 2026-12-14 | 70 | 90%
3.1 | Store layout to brand standard | Store design | 2026-10-06 | 2026-11-04 | 30 | 100%
3.2 | Shopfront & signage design | Store design | 2026-10-26 | 2026-11-19 | 25 | 100%
3.3 | Landlord & centre approval | Property | 2026-11-05 | 2026-11-29 | 25 | 80%
3.4 | Building & signage permits | Consultant | 2026-11-15 | 2026-12-14 | 30 | 60%
4 | Approvals granted |  | 2026-12-15 | 2026-12-15 | — | —
5 | Fit-out |  | 2026-12-15 | 2027-03-04 | 80 | 20%
6 | Landlord handover of unit |  | 2026-12-15 | 2026-12-15 | — | —
6.1 | Shopfitting & partitions | Shopfitter | 2026-12-15 | 2027-01-13 | 30 | 30%
6.2 | Flooring & lighting | Shopfitter | 2027-01-07 | 2027-01-28 | 22 | 10%
6.3 | Fixtures & shelving install | Shopfitter | 2027-01-24 | 2027-02-12 | 20 | 0%
6.4 | Shopfront & signage install | Signage | 2027-02-08 | 2027-02-22 | 15 | 0%
6.5 | Snagging | Shopfitter | 2027-02-23 | 2027-03-04 | 10 | 0%
7 | Licensing, systems & loss prevention |  | 2026-10-11 | 2027-03-14 | 155 | 40%
7.1 | Trading licence & registrations | Operations | 2026-10-11 | 2026-11-24 | 45 | 100%
7.2 | POS & payment terminals | IT | 2027-01-24 | 2027-02-17 | 25 | 0%

## Slide 4
7.3 | Network & CCTV install | IT | 2027-01-29 | 2027-02-22 | 25 | 0%
7.4 | Security tagging & loss prevention | Loss prevention | 2027-02-13 | 2027-02-27 | 15 | 0%
7.5 | Fire & accessibility inspection | Inspector | 2027-03-02 | 2027-03-09 | 8 | 0%
8 | Cleared to trade |  | 2027-03-12 | 2027-03-12 | — | —
9 | Inventory & merchandising |  | 2026-12-10 | 2027-03-19 | 100 | 25%
10 | Opening order placed |  | 2026-12-10 | 2026-12-10 | — | —
10.1 | Supplier lead time & production | Buying | 2026-12-10 | 2027-02-17 | 70 | 40%
10.2 | Stock delivery & back-of-house set-up | Store team | 2027-02-18 | 2027-03-01 | 12 | 0%
10.3 | Planogram build | Visual merchandising | 2027-02-08 | 2027-02-25 | 18 | 0%
10.4 | Visual merchandising install | Visual merchandising | 2027-03-02 | 2027-03-15 | 14 | 0%
11 | Hiring, training & launch |  | 2026-12-25 | 2027-03-24 | 90 | 15%
11.1 | Store manager hired | HR | 2026-12-25 | 2027-01-23 | 30 | 60%
11.2 | Floor team recruitment | Store manager | 2027-01-24 | 2027-02-22 | 30 | 0%
11.3 | Product & POS training | Store manager | 2027-02-23 | 2027-03-09 | 15 | 0%
11.4 | Local marketing & launch comms | Marketing | 2027-02-08 | 2027-03-19 | 40 | 0%
11.5 | Soft launch trading days | Store team | 2027-03-16 | 2027-03-20 | 5 | 0%
12 | Grand opening |  | 2027-03-25 | 2027-03-25 | — | —