## Gantt
RFP Procurement Timeline
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2
1 | Requirements & business case |  | 2026-08-02 | 2026-09-30 | 60
1.1 | Requirements gathering with stakeholders | Category manager | 2026-08-02 | 2026-08-26 | 25
1.2 | Business case & budget approval | Finance | 2026-08-22 | 2026-09-15 | 25
1.3 | Procurement route & threshold check | Procurement | 2026-09-01 | 2026-09-15 | 15
1.4 | Evaluation criteria & weightings agreed | Procurement | 2026-09-16 | 2026-09-30 | 15
2 | ◆ Approval to go to market |  | 2026-10-01 | 2026-10-01 | [9 empty] | ◆
3 | Market engagement & documents |  | 2026-09-11 | 2026-11-09 | 60
3.1 | Supplier market research | Category manager | 2026-09-11 | 2026-09-30 | 20
3.2 | Prior information notice or RFI | Procurement | 2026-09-26 | 2026-10-15 | 20
3.3 | RFP document drafting | Procurement | 2026-10-01 | 2026-10-30 | 30
3.4 | Contract terms & schedules drafted | Legal | 2026-10-11 | 2026-11-04 | 25
3.5 | Scoring model & moderation rules | Procurement | 2026-10-26 | 2026-11-09 | 15
3.6 | Evaluation panel confirmed & diaries blocked | Procurement | 2026-10-31 | 2026-11-09 | 10
4 | ◆ Tender pack approved |  | 2026-11-10 | 2026-11-10 | [15 empty] | ◆
5 | Open tender period |  | 2026-11-10 | 2026-12-29 | 50
6 | ◆ RFP issued to market |  | 2026-11-10 | 2026-11-10 | [15 empty] | ◆
6.1 | Bidder question window | Bidders | 2026-11-10 | 2026-12-04 | 25
6.2 | Supplier briefing session | Procurement | 2026-11-20 | 2026-11-20 | 1
7 | ◆ Clarification deadline |  | 2026-12-05 | 2026-12-05 | [18 empty] | ◆
7.1 | Answers published to all bidders | Procurement | 2026-12-05 | 2026-12-11 | 7
7.2 | Bid preparation period | Bidders | 2026-12-12 | 2026-12-29 | 18
8 | ◆ Submission deadline |  | 2026-12-30 | 2026-12-30 | [22 empty] | ◆
9 | Evaluation |  | 2026-12-30 | 2027-03-11 | 72
9.1 | Compliance & completeness check | Procurement | 2026-12-30 | 2027-01-05 | 7
9.2 | Technical evaluation by panel | Evaluation panel | 2027-01-06 | 2027-01-25 | 20
9.3 | Commercial evaluation & cost modelling | Finance | 2027-01-06 | 2027-01-23 | 18
9.4 | Moderation & consensus scoring | Evaluation panel | 2027-01-27 | 2027-02-05 | 10
9.5 | Supplier presentations or demos | Evaluation panel | 2027-02-06 | 2027-02-13 | 8
9.6 | Due diligence on preferred bidder | Finance & legal | 2027-02-18 | 2027-02-27 | 10
9.7 | Evaluation report & recommendation | Procurement | 2027-02-28 | 2027-03-09 | 10
10 | ◆ Award recommendation approved |  | 2027-03-12 | 2027-03-12 | [32 empty] | ◆
11 | Award, standstill & contract |  | 2027-03-12 | 2027-04-26 | 46
11.1 | Award & regret letters issued | Procurement | 2027-03-12 | 2027-03-14 | 3
11.2 | Standstill or notice period | Procurement | 2027-03-15 | 2027-03-26 | 12
11.3 | Debrief unsuccessful bidders | Procurement | 2027-03-18 | 2027-03-25 | 8
11.4 | Final contract negotiation | Legal | 2027-03-27 | 2027-04-20 | 25
11.5 | Contract signature | Legal | 2027-04-24 | 2027-04-26 | 3
12 | ◆ Contract awarded |  | 2027-04-27 | 2027-04-27 | [39 empty] | ◆
13 | Mobilisation & transition |  | 2027-04-27 | 2027-08-01 | 97
13.1 | Mobilisation plan & kickoff | Supplier & business | 2027-04-27 | 2027-05-11 | 15
13.2 | Transition from incumbent supplier | Supplier | 2027-05-12 | 2027-06-25 | 45
13.3 | Onboarding, access & systems setup | IT | 2027-05-19 | 2027-06-17 | 30
13.4 | Governance & KPI reporting set up | Contract manager | 2027-06-18 | 2027-07-07 | 20
14 | ◆ Service commencement |  | 2027-07-13 | 2027-07-13 | [50 empty] | ◆
14.1 | First contract review | Contract manager | 2027-07-23 | 2027-08-01 | 10