## Slide 1
Road Construction Schedule
Free Gantt chart template · gantts.app

## Slide 2
Road Construction Schedule
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Survey & design
Topographic & ground investigation
Utility record search & trial holes
Preliminary design
Detailed design & drainage
Road safety audit stage 1-2
◆ Design approved
Land & consents
Land referencing
Land acquisition & possession
Planning & environmental consent
Side road orders
◆ Consents in place
Utilities diversions
C3 / C4 estimates requested
Diversion design & programming
Gas main diversion
Water main diversion
HV / LV electricity diversion
Telecoms diversion
◆ Diversions complete
Traffic management
TM design & approval
Road space booking & permits
Diversion route agreement
TM stage 1 - lane closures
TM stage 2 - contraflow
TM stage 3 - night closures
Earthworks & drainage
Site clearance & topsoil strip
Cut & fill earthworks
Carrier drains & outfalls
Gullies & attenuation
Capping layer
Pavement construction
Sub-base
Kerbs & footways
Base course
Binder course
Ironwork adjustment
Surface course
◆ Surfacing complete
Signage, markings & handover
Street lighting & ducting
Road markings & studs
Signs, gantries & safety fencing
Road safety audit stage 3
Snagging & handover
◆ Road open to traffic
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Survey & design |  | 2026-08-02 | 2026-12-19 | 140 | 100%
1.1 | Topographic & ground investigation | Surveyor | 2026-08-02 | 2026-09-15 | 45 | 100%
1.2 | Utility record search & trial holes | Surveyor | 2026-08-22 | 2026-10-05 | 45 | 100%
1.3 | Preliminary design | Designer | 2026-09-16 | 2026-10-30 | 45 | 100%
1.4 | Detailed design & drainage | Designer | 2026-10-26 | 2026-12-19 | 55 | 100%
1.5 | Road safety audit stage 1-2 | Auditor | 2026-11-30 | 2026-12-19 | 20 | 100%
2 | Design approved |  | 2026-12-25 | 2026-12-25 | — | —
3 | Land & consents |  | 2026-09-01 | 2027-02-22 | 175 | 90%
3.1 | Land referencing | Land agent | 2026-09-01 | 2026-10-10 | 40 | 100%
3.2 | Land acquisition & possession | Land agent | 2026-10-11 | 2027-01-08 | 90 | 90%
3.3 | Planning & environmental consent | Consultant | 2026-10-31 | 2027-01-23 | 85 | 80%
3.4 | Side road orders | Legal | 2026-11-30 | 2027-02-22 | 85 | 70%
4 | Consents in place |  | 2027-02-23 | 2027-02-23 | — | —
5 | Utilities diversions |  | 2026-10-01 | 2027-05-28 | 240 | 30%
5.1 | C3 / C4 estimates requested | Utilities coordinator | 2026-10-01 | 2026-11-29 | 60 | 100%
5.2 | Diversion design & programming | Utilities coordinator | 2026-12-10 | 2027-02-17 | 70 | 60%
5.3 | Gas main diversion | Gas undertaker | 2027-02-23 | 2027-04-18 | 55 | 0%
5.4 | Water main diversion | Water undertaker | 2027-03-10 | 2027-04-23 | 45 | 0%
5.5 | HV / LV electricity diversion | DNO | 2027-03-25 | 2027-05-13 | 50 | 0%
5.6 | Telecoms diversion | Telecoms operator | 2027-04-19 | 2027-05-28 | 40 | 0%
6 | Diversions complete |  | 2027-05-29 | 2027-05-29 | — | —

## Slide 4
7 | Traffic management |  | 2026-12-30 | 2027-11-14 | 320 | 20%
7.1 | TM design & approval | TM designer | 2026-12-30 | 2027-02-07 | 40 | 80%
7.2 | Road space booking & permits | Contractor | 2027-02-03 | 2027-03-09 | 35 | 60%
7.3 | Diversion route agreement | Highway authority | 2027-02-18 | 2027-03-19 | 30 | 40%
7.4 | TM stage 1 - lane closures | TM contractor | 2027-02-28 | 2027-06-17 | 110 | 10%
7.5 | TM stage 2 - contraflow | TM contractor | 2027-06-18 | 2027-09-25 | 100 | 0%
7.6 | TM stage 3 - night closures | TM contractor | 2027-09-26 | 2027-11-14 | 50 | 0%
8 | Earthworks & drainage |  | 2027-02-28 | 2027-08-26 | 180 | 5%
8.1 | Site clearance & topsoil strip | Civil | 2027-02-28 | 2027-03-29 | 30 | 20%
8.2 | Cut & fill earthworks | Civil | 2027-03-30 | 2027-06-17 | 80 | 0%
8.3 | Carrier drains & outfalls | Drainage | 2027-05-29 | 2027-07-27 | 60 | 0%
8.4 | Gullies & attenuation | Drainage | 2027-07-13 | 2027-08-26 | 45 | 0%
8.5 | Capping layer | Civil | 2027-06-28 | 2027-08-11 | 45 | 0%
9 | Pavement construction |  | 2027-08-12 | 2027-12-04 | 115 | 0%
9.1 | Sub-base | Civil | 2027-08-12 | 2027-09-20 | 40 | 0%
9.2 | Kerbs & footways | Civil | 2027-09-06 | 2027-10-20 | 45 | 0%
9.3 | Base course | Surfacing | 2027-09-21 | 2027-10-20 | 30 | 0%
9.4 | Binder course | Surfacing | 2027-10-19 | 2027-11-12 | 25 | 0%
9.5 | Ironwork adjustment | Civil | 2027-11-05 | 2027-11-19 | 15 | 0%
9.6 | Surface course | Surfacing | 2027-11-17 | 2027-12-04 | 18 | 0%
10 | Surfacing complete |  | 2027-12-05 | 2027-12-05 | — | —
11 | Signage, markings & handover |  | 2027-11-15 | 2028-01-28 | 75 | 0%
11.1 | Street lighting & ducting | Electrical | 2027-11-15 | 2027-12-19 | 35 | 0%
11.2 | Road markings & studs | Specialist | 2027-12-05 | 2027-12-24 | 20 | 0%

## Slide 5
11.3 | Signs, gantries & safety fencing | Specialist | 2027-12-10 | 2028-01-08 | 30 | 0%
11.4 | Road safety audit stage 3 | Auditor | 2028-01-09 | 2028-01-20 | 12 | 0%
11.5 | Snagging & handover | Contractor | 2028-01-14 | 2028-01-28 | 15 | 0%
12 | Road open to traffic |  | 2028-01-29 | 2028-01-29 | — | —