## Gantt
Road Construction Schedule
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31
1 | Survey & design |  | 2026-08-02 | 2026-12-19 | 140
1.1 | Topographic & ground investigation | Surveyor | 2026-08-02 | 2026-09-15 | 45
1.2 | Utility record search & trial holes | Surveyor | 2026-08-22 | 2026-10-05 | 45
1.3 | Preliminary design | Designer | 2026-09-16 | 2026-10-30 | 45
1.4 | Detailed design & drainage | Designer | 2026-10-26 | 2026-12-19 | 55
1.5 | Road safety audit stage 1-2 | Auditor | 2026-11-30 | 2026-12-19 | 20
2 | ◆ Design approved |  | 2026-12-25 | 2026-12-25 | [21 empty] | ◆
3 | Land & consents |  | 2026-09-01 | 2027-02-22 | 175
3.1 | Land referencing | Land agent | 2026-09-01 | 2026-10-10 | 40
3.2 | Land acquisition & possession | Land agent | 2026-10-11 | 2027-01-08 | 90
3.3 | Planning & environmental consent | Consultant | 2026-10-31 | 2027-01-23 | 85
3.4 | Side road orders | Legal | 2026-11-30 | 2027-02-22 | 85
4 | ◆ Consents in place |  | 2027-02-23 | 2027-02-23 | [30 empty] | ◆
5 | Utilities diversions |  | 2026-10-01 | 2027-05-28 | 240
5.1 | C3 / C4 estimates requested | Utilities coordinator | 2026-10-01 | 2026-11-29 | 60
5.2 | Diversion design & programming | Utilities coordinator | 2026-12-10 | 2027-02-17 | 70
5.3 | Gas main diversion | Gas undertaker | 2027-02-23 | 2027-04-18 | 55
5.4 | Water main diversion | Water undertaker | 2027-03-10 | 2027-04-23 | 45
5.5 | HV / LV electricity diversion | DNO | 2027-03-25 | 2027-05-13 | 50
5.6 | Telecoms diversion | Telecoms operator | 2027-04-19 | 2027-05-28 | 40
6 | ◆ Diversions complete |  | 2027-05-29 | 2027-05-29 | [43 empty] | ◆
7 | Traffic management |  | 2026-12-30 | 2027-11-14 | 320
7.1 | TM design & approval | TM designer | 2026-12-30 | 2027-02-07 | 40
7.2 | Road space booking & permits | Contractor | 2027-02-03 | 2027-03-09 | 35
7.3 | Diversion route agreement | Highway authority | 2027-02-18 | 2027-03-19 | 30
7.4 | TM stage 1 - lane closures | TM contractor | 2027-02-28 | 2027-06-17 | 110
7.5 | TM stage 2 - contraflow | TM contractor | 2027-06-18 | 2027-09-25 | 100
7.6 | TM stage 3 - night closures | TM contractor | 2027-09-26 | 2027-11-14 | 50
8 | Earthworks & drainage |  | 2027-02-28 | 2027-08-26 | 180
8.1 | Site clearance & topsoil strip | Civil | 2027-02-28 | 2027-03-29 | 30
8.2 | Cut & fill earthworks | Civil | 2027-03-30 | 2027-06-17 | 80
8.3 | Carrier drains & outfalls | Drainage | 2027-05-29 | 2027-07-27 | 60
8.4 | Gullies & attenuation | Drainage | 2027-07-13 | 2027-08-26 | 45
8.5 | Capping layer | Civil | 2027-06-28 | 2027-08-11 | 45
9 | Pavement construction |  | 2027-08-12 | 2027-12-04 | 115
9.1 | Sub-base | Civil | 2027-08-12 | 2027-09-20 | 40
9.2 | Kerbs & footways | Civil | 2027-09-06 | 2027-10-20 | 45
9.3 | Base course | Surfacing | 2027-09-21 | 2027-10-20 | 30
9.4 | Binder course | Surfacing | 2027-10-19 | 2027-11-12 | 25
9.5 | Ironwork adjustment | Civil | 2027-11-05 | 2027-11-19 | 15
9.6 | Surface course | Surfacing | 2027-11-17 | 2027-12-04 | 18
10 | ◆ Surfacing complete |  | 2027-12-05 | 2027-12-05 | [71 empty] | ◆
11 | Signage, markings & handover |  | 2027-11-15 | 2028-01-28 | 75
11.1 | Street lighting & ducting | Electrical | 2027-11-15 | 2027-12-19 | 35
11.2 | Road markings & studs | Specialist | 2027-12-05 | 2027-12-24 | 20
11.3 | Signs, gantries & safety fencing | Specialist | 2027-12-10 | 2028-01-08 | 30
11.4 | Road safety audit stage 3 | Auditor | 2028-01-09 | 2028-01-20 | 12
11.5 | Snagging & handover | Contractor | 2028-01-14 | 2028-01-28 | 15
12 | ◆ Road open to traffic |  | 2028-01-29 | 2028-01-29 | [78 empty] | ◆