## Slide 1
S-Curve Progress Tracking
Free Gantt chart template · gantts.app

## Slide 2
S-Curve Progress Tracking
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Initiation & baseline
Project charter & scope
Budget & funding approval
Schedule development
◆ Baseline set
Design & engineering
Concept design
Detailed design
Design review & approval
◆ Design frozen
Procurement
Tender & vendor selection
Long-lead orders placed
Long-lead deliveries
Bulk materials delivery
Construction & build
Site mobilization
Civil & foundations
Structure & envelope
Mechanical & electrical install
Fit-out & finishes
◆ Construction complete
Testing & commissioning
Pre-commissioning checks
Functional testing
Snagging & rectification
◆ Commissioning complete
Handover & close-out
As-built documentation
Client handover & training
Final account & lessons learned
◆ Project closed
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Initiation & baseline |  | 2026-08-02 | 2026-09-15 | 45 | 100%
1.1 | Project charter & scope | PM | 2026-08-02 | 2026-08-21 | 20 | 100%
1.2 | Budget & funding approval | Finance | 2026-08-17 | 2026-09-05 | 20 | 100%
1.3 | Schedule development | Planner | 2026-08-27 | 2026-09-15 | 20 | 100%
2 | Baseline set |  | 2026-09-16 | 2026-09-16 | — | —
3 | Design & engineering |  | 2026-09-16 | 2026-12-14 | 90 | 100%
3.1 | Concept design | Engineering | 2026-09-16 | 2026-10-15 | 30 | 100%
3.2 | Detailed design | Engineering | 2026-10-13 | 2026-12-11 | 60 | 100%
3.3 | Design review & approval | Client | 2026-11-30 | 2026-12-14 | 15 | 100%
4 | Design frozen |  | 2026-12-15 | 2026-12-15 | — | —
5 | Procurement |  | 2026-11-20 | 2027-03-09 | 110 | 85%
5.1 | Tender & vendor selection | Procurement | 2026-11-20 | 2026-12-29 | 40 | 100%
5.2 | Long-lead orders placed | Procurement | 2026-12-25 | 2027-01-08 | 15 | 100%
5.3 | Long-lead deliveries | Supplier | 2027-01-09 | 2027-03-09 | 60 | 70%
5.4 | Bulk materials delivery | Supplier | 2027-01-24 | 2027-03-09 | 45 | 80%
6 | Construction & build |  | 2026-12-30 | 2027-06-27 | 180 | 55%
6.1 | Site mobilization | Contractor | 2026-12-30 | 2027-01-18 | 20 | 100%
6.2 | Civil & foundations | Civil | 2027-01-17 | 2027-03-12 | 55 | 100%
6.3 | Structure & envelope | Structural | 2027-03-05 | 2027-05-18 | 75 | 60%
6.4 | Mechanical & electrical install | MEP | 2027-04-09 | 2027-06-17 | 70 | 30%
6.5 | Fit-out & finishes | Contractor | 2027-05-14 | 2027-06-27 | 45 | 10%

## Slide 4
7 | Construction complete |  | 2027-06-28 | 2027-06-28 | — | —
8 | Testing & commissioning |  | 2027-06-18 | 2027-08-26 | 70 | 0%
8.1 | Pre-commissioning checks | Commissioning | 2027-06-18 | 2027-07-12 | 25 | 0%
8.2 | Functional testing | Commissioning | 2027-07-10 | 2027-08-08 | 30 | 0%
8.3 | Snagging & rectification | Contractor | 2027-07-28 | 2027-08-26 | 30 | 0%
9 | Commissioning complete |  | 2027-08-27 | 2027-08-27 | — | —
10 | Handover & close-out |  | 2027-08-17 | 2027-10-05 | 50 | 0%
10.1 | As-built documentation | Engineering | 2027-08-17 | 2027-09-15 | 30 | 0%
10.2 | Client handover & training | PM | 2027-08-27 | 2027-09-15 | 20 | 0%
10.3 | Final account & lessons learned | PM | 2027-09-11 | 2027-10-05 | 25 | 0%
11 | Project closed |  | 2027-10-06 | 2027-10-06 | — | —