## Gantt
S-Curve Progress Tracking
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11
1 | Initiation & baseline |  | 2026-08-02 | 2026-09-15 | 45
1.1 | Project charter & scope | PM | 2026-08-02 | 2026-08-21 | 20
1.2 | Budget & funding approval | Finance | 2026-08-17 | 2026-09-05 | 20
1.3 | Schedule development | Planner | 2026-08-27 | 2026-09-15 | 20
2 | ◆ Baseline set |  | 2026-09-16 | 2026-09-16 | [7 empty] | ◆
3 | Design & engineering |  | 2026-09-16 | 2026-12-14 | 90
3.1 | Concept design | Engineering | 2026-09-16 | 2026-10-15 | 30
3.2 | Detailed design | Engineering | 2026-10-13 | 2026-12-11 | 60
3.3 | Design review & approval | Client | 2026-11-30 | 2026-12-14 | 15
4 | ◆ Design frozen |  | 2026-12-15 | 2026-12-15 | [20 empty] | ◆
5 | Procurement |  | 2026-11-20 | 2027-03-09 | 110
5.1 | Tender & vendor selection | Procurement | 2026-11-20 | 2026-12-29 | 40
5.2 | Long-lead orders placed | Procurement | 2026-12-25 | 2027-01-08 | 15
5.3 | Long-lead deliveries | Supplier | 2027-01-09 | 2027-03-09 | 60
5.4 | Bulk materials delivery | Supplier | 2027-01-24 | 2027-03-09 | 45
6 | Construction & build |  | 2026-12-30 | 2027-06-27 | 180
6.1 | Site mobilization | Contractor | 2026-12-30 | 2027-01-18 | 20
6.2 | Civil & foundations | Civil | 2027-01-17 | 2027-03-12 | 55
6.3 | Structure & envelope | Structural | 2027-03-05 | 2027-05-18 | 75
6.4 | Mechanical & electrical install | MEP | 2027-04-09 | 2027-06-17 | 70
6.5 | Fit-out & finishes | Contractor | 2027-05-14 | 2027-06-27 | 45
7 | ◆ Construction complete |  | 2027-06-28 | 2027-06-28 | [48 empty] | ◆
8 | Testing & commissioning |  | 2027-06-18 | 2027-08-26 | 70
8.1 | Pre-commissioning checks | Commissioning | 2027-06-18 | 2027-07-12 | 25
8.2 | Functional testing | Commissioning | 2027-07-10 | 2027-08-08 | 30
8.3 | Snagging & rectification | Contractor | 2027-07-28 | 2027-08-26 | 30
9 | ◆ Commissioning complete |  | 2027-08-27 | 2027-08-27 | [56 empty] | ◆
10 | Handover & close-out |  | 2027-08-17 | 2027-10-05 | 50
10.1 | As-built documentation | Engineering | 2027-08-17 | 2027-09-15 | 30
10.2 | Client handover & training | PM | 2027-08-27 | 2027-09-15 | 20
10.3 | Final account & lessons learned | PM | 2027-09-11 | 2027-10-05 | 25
11 | ◆ Project closed |  | 2027-10-06 | 2027-10-06 | [62 empty] | ◆