## Gantt
SAP S/4HANA Migration Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21
1 | Path decision & readiness |  | 2026-08-02 | 2026-10-10 | 70
1.1 | Run readiness check & simplification item report | Basis | 2026-08-02 | 2026-08-21 | 20
1.2 | Business case & scope definition | Programme lead | 2026-08-12 | 2026-09-05 | 25
1.3 | Brownfield vs greenfield decision | Steering group | 2026-09-01 | 2026-09-15 | 15
1.4 | Sizing & target landscape design | Architect | 2026-09-11 | 2026-09-30 | 20
2 | ◆ Conversion path signed off |  | 2026-10-11 | 2026-10-11 | [11 empty] | ◆
3 | Preparation & custom code remediation |  | 2026-10-11 | 2027-03-09 | 150
3.1 | Custom code analysis against simplification database | ABAP lead | 2026-10-11 | 2026-11-09 | 30
3.2 | Triage & classify remediation findings | ABAP lead | 2026-11-05 | 2026-11-29 | 25
3.3 | Retire obsolete custom objects | ABAP team | 2026-11-25 | 2026-12-29 | 35
3.4 | Remediation wave 1 — finance objects | ABAP team | 2026-11-30 | 2027-01-18 | 50
3.5 | Remediation wave 2 — logistics objects | ABAP team | 2027-01-04 | 2027-02-22 | 50
3.6 | Customer-vendor integration preparation | Master data | 2026-11-10 | 2026-12-19 | 40
3.7 | New asset accounting & finance data model prep | Finance | 2026-12-10 | 2027-02-02 | 55
3.8 | Master data cleansing programme | Master data | 2026-11-20 | 2027-02-17 | 90
4 | ◆ Custom code remediation complete |  | 2027-03-10 | 2027-03-10 | [32 empty] | ◆
5 | Sandbox & development conversion |  | 2027-02-18 | 2027-06-07 | 110
5.1 | Sandbox technical conversion run | Basis | 2027-02-18 | 2027-03-09 | 20
5.2 | Development system conversion | Basis | 2027-03-25 | 2027-04-08 | 15
5.3 | Functional adaptation in development | Functional team | 2027-04-09 | 2027-05-13 | 35
5.4 | Fiori apps & role redesign | Security | 2027-04-14 | 2027-05-23 | 40
5.5 | Quality system conversion | Basis | 2027-05-14 | 2027-05-28 | 15
6 | ◆ Quality system converted |  | 2027-05-29 | 2027-05-29 | [43 empty] | ◆
7 | Test cycles |  | 2027-05-29 | 2027-09-10 | 105
7.1 | Functional unit testing | Functional team | 2027-05-29 | 2027-06-22 | 25
7.2 | Interface & integration testing | Integration team | 2027-06-13 | 2027-07-22 | 40
7.3 | Authorisation & role testing | Security | 2027-06-23 | 2027-07-22 | 30
7.4 | Performance & volume testing | Basis | 2027-07-13 | 2027-08-11 | 30
7.5 | Defect fix & retest loop | All teams | 2027-06-28 | 2027-08-31 | 65
7.6 | End user training build & delivery | Change lead | 2027-07-18 | 2027-09-10 | 55
8 | ◆ Integration test exit passed |  | 2027-09-06 | 2027-09-06 | [58 empty] | ◆
9 | Mock cutovers & dress rehearsal |  | 2027-08-17 | 2027-12-04 | 110
9.1 | Cutover runbook drafted | Cutover manager | 2027-08-17 | 2027-09-05 | 20
9.2 | Mock cutover 1 — discover gaps | Cutover team | 2027-09-06 | 2027-09-17 | 12
9.3 | Runbook rework after mock 1 | Cutover manager | 2027-09-18 | 2027-10-02 | 15
9.4 | Mock cutover 2 — timed full volume | Cutover team | 2027-10-06 | 2027-10-17 | 12
9.5 | Mock cutover 3 — rehearse roles & handovers | Cutover team | 2027-10-31 | 2027-11-11 | 12
9.6 | Dress rehearsal on production copy | Cutover team | 2027-11-15 | 2027-11-28 | 14
10 | ◆ Dress rehearsal go/no-go decision |  | 2027-12-05 | 2027-12-05 | [71 empty] | ◆
11 | Freeze, cutover & hypercare |  | 2027-12-05 | 2028-02-17 | 75
11.1 | Business freeze communication & readiness | Change lead | 2027-11-15 | 2027-12-04 | 20
11.2 | Business freeze window opens | Business owners | 2027-12-07 | 2027-12-18 | 12
11.3 | Production system conversion | Basis | 2027-12-13 | 2027-12-17 | 5
11.4 | Validation & financial reconciliation | Finance | 2027-12-18 | 2027-12-23 | 6
11.5 | Release to business & freeze lifted | Programme lead | 2027-12-24 | 2027-12-25 | 2
11.6 | Hypercare support & defect burn-down | Support team | 2027-12-26 | 2028-02-08 | 45
11.7 | First period close on S/4HANA | Finance | 2028-01-14 | 2028-01-23 | 10
12 | ◆ Hypercare exit |  | 2028-02-13 | 2028-02-13 | [81 empty] | ◆