## Slide 1
School Year Planning Calendar
Free Gantt chart template · gantts.app

## Slide 2
School Year Planning Calendar
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Curriculum & timetable
Curriculum model & option blocks
Option choices & setting
Subject & staff allocation
Timetable build & validation
Rooming & resource allocation
◆ Timetable published
Staffing & contracts
Establishment & budget review
◆ Resignation deadline
Recruitment rounds
Contracts issued
Cover & supply arrangements
New staff induction
Admissions & enrolment
Open evenings
Application window
Offers & appeals
Transition days
Enrolment & roll confirmation
◆ Roll confirmed
Term dates & calendar
Term & holiday dates agreed
INSET days scheduled
Calendar of events published
Parent communications
◆ Autumn term starts
Assessment & exams
Baseline assessment
Exam entries & deadlines
Mock exam series
Access arrangements & invigilation
Public exam series
◆ Results day
Reporting & parents
Data collection point 1
Autumn reports & parents evening
Data collection point 2
Spring reports & parents evening
Summer reports & target setting
Inspection & governance
Self-evaluation review
Governor meeting cycle
Safeguarding audit
Policy review schedule
Inspection readiness review
Budget cycle
◆ Funding allocation received
Budget build & approval
In-year budget monitoring
Year-end return
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Curriculum & timetable |  | 2026-08-02 | 2026-12-29 | 150 | 100%
1.1 | Curriculum model & option blocks | Deputy head | 2026-08-02 | 2026-09-10 | 40 | 100%
1.2 | Option choices & setting | Heads of year | 2026-09-06 | 2026-10-10 | 35 | 100%
1.3 | Subject & staff allocation | Deputy head | 2026-10-11 | 2026-11-19 | 40 | 100%
1.4 | Timetable build & validation | Timetabler | 2026-11-15 | 2026-12-24 | 40 | 90%
1.5 | Rooming & resource allocation | Timetabler | 2026-12-10 | 2026-12-29 | 20 | 60%
2 | Timetable published |  | 2026-12-30 | 2026-12-30 | — | —
3 | Staffing & contracts |  | 2026-08-02 | 2027-01-23 | 175 | 80%
3.1 | Establishment & budget review | Business manager | 2026-08-02 | 2026-09-05 | 35 | 100%
4 | Resignation deadline |  | 2026-09-16 | 2026-09-16 | — | —
4.1 | Recruitment rounds | HR | 2026-09-16 | 2026-11-29 | 75 | 80%
4.2 | Contracts issued | HR | 2026-11-25 | 2026-12-19 | 25 | 40%
4.3 | Cover & supply arrangements | Cover manager | 2026-12-20 | 2027-01-23 | 35 | 20%
4.4 | New staff induction | Deputy head | 2027-01-04 | 2027-01-23 | 20 | 0%
5 | Admissions & enrolment |  | 2026-08-02 | 2027-02-27 | 210 | 60%
5.1 | Open evenings | Admissions | 2026-08-02 | 2026-08-21 | 20 | 100%
5.2 | Application window | Admissions | 2026-08-17 | 2026-10-10 | 55 | 100%
5.3 | Offers & appeals | Admissions | 2026-10-11 | 2026-12-09 | 60 | 60%
5.4 | Transition days | Heads of year | 2026-12-20 | 2026-12-29 | 10 | 0%
5.5 | Enrolment & roll confirmation | Admissions | 2027-01-24 | 2027-02-27 | 35 | 0%
6 | Roll confirmed |  | 2027-02-28 | 2027-02-28 | — | —

## Slide 4
7 | Term dates & calendar |  | 2026-08-02 | 2027-02-07 | 190 | 70%
7.1 | Term & holiday dates agreed | Governors | 2026-08-02 | 2026-08-26 | 25 | 100%
7.2 | INSET days scheduled | Head | 2026-08-27 | 2026-09-10 | 15 | 100%
7.3 | Calendar of events published | Office | 2026-12-30 | 2027-01-18 | 20 | 30%
7.4 | Parent communications | Office | 2027-01-19 | 2027-02-07 | 20 | 0%
8 | Autumn term starts |  | 2027-02-13 | 2027-02-13 | — | —
9 | Assessment & exams |  | 2027-02-13 | 2027-12-09 | 300 | 0%
9.1 | Baseline assessment | Teaching staff | 2027-02-18 | 2027-03-04 | 15 | 0%
9.2 | Exam entries & deadlines | Exams officer | 2027-04-09 | 2027-05-18 | 40 | 0%
9.3 | Mock exam series | Exams officer | 2027-05-29 | 2027-06-17 | 20 | 0%
9.4 | Access arrangements & invigilation | Exams officer | 2027-06-18 | 2027-08-01 | 45 | 0%
9.5 | Public exam series | Exams officer | 2027-09-26 | 2027-11-09 | 45 | 0%
10 | Results day |  | 2027-12-10 | 2027-12-10 | — | —
11 | Reporting & parents |  | 2027-03-20 | 2027-11-24 | 250 | 0%
11.1 | Data collection point 1 | Teaching staff | 2027-03-20 | 2027-03-29 | 10 | 0%
11.2 | Autumn reports & parents evening | Heads of year | 2027-04-09 | 2027-05-03 | 25 | 0%
11.3 | Data collection point 2 | Teaching staff | 2027-07-08 | 2027-07-17 | 10 | 0%
11.4 | Spring reports & parents evening | Heads of year | 2027-07-23 | 2027-08-16 | 25 | 0%
11.5 | Summer reports & target setting | Heads of year | 2027-10-31 | 2027-11-24 | 25 | 0%
12 | Inspection & governance |  | 2027-02-13 | 2027-11-29 | 290 | 0%
12.1 | Self-evaluation review | Leadership | 2027-02-13 | 2027-03-24 | 40 | 0%
12.2 | Governor meeting cycle | Governors | 2027-02-28 | 2027-11-29 | 275 | 0%
12.3 | Safeguarding audit | DSL | 2027-04-19 | 2027-05-08 | 20 | 0%
12.4 | Policy review schedule | Leadership | 2027-05-29 | 2027-07-27 | 60 | 0%

## Slide 5
12.5 | Inspection readiness review | Leadership | 2027-08-07 | 2027-08-26 | 20 | 0%
13 | Budget cycle |  | 2026-08-02 | 2027-11-24 | 480 | 40%
14 | Funding allocation received |  | 2026-08-02 | 2026-08-02 | — | —
14.1 | Budget build & approval | Business manager | 2026-08-12 | 2026-10-20 | 70 | 90%
14.2 | In-year budget monitoring | Business manager | 2027-02-13 | 2027-11-09 | 270 | 0%
14.3 | Year-end return | Business manager | 2027-11-10 | 2027-11-24 | 15 | 0%