## Slide 1
Semiconductor Fab Construction
Free Gantt chart template · gantts.app

## Slide 2
Semiconductor Fab Construction
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Jun 5
Jun 19
Jul 3
Jul 17
Jul 31
Aug 14
Aug 28
Sep 11
Sep 25
Oct 9
Oct 23
Nov 6
Nov 20
Site, permits & base build
Site selection & seismic/vibration survey
Environmental permits & hazardous materials licence
Fab basis of design & tool set freeze
Long-lead utility equipment procurement
Piling & vibration-isolated waffle slab
◆ Tool set frozen
◆ Permits granted
Shell & cleanroom envelope
Structural steel & building envelope
Subfab & waffle slab penetrations
Roof, weathertight & building dry-in
◆ Building dry-in complete
Cleanroom wall & ceiling grid installation
Raised access floor & perforated tiles
Fan filter unit installation
Facility utilities & abatement
Ultrapure water plant installation
UPW loop flush & resistivity qualification
Bulk & specialty gas yard construction
Gas distribution, VMB & leak testing
Exhaust, scrubber & abatement systems
Electrical substation & UPS energisation
◆ Facility utilities available at hook-up points
Cleanroom certification & protocol changeover
Cleanroom construction protocol changeover
Gowning, airlocks & material entry procedures live
Air balancing & laminar flow verification
Particle count & ISO class certification
Vibration, EMI & acoustic survey
◆ Cleanroom certified to ISO class
Tool move-in, hook-up & qualification
Tool delivery sequence & rigging plan
Litho tool move-in & set
Etch & deposition tool move-in
Metrology & inspection tool move-in
Tool hook-up to gases, exhaust & UPW
Tool power-up & vendor installation qualification
Operational qualification & SPC baseline
◆ Tool qualification complete
Process qualification & first silicon
MES, automation & AMHS integration
Recipe loading & process module setup
First wafer through single module
Full process flow pilot lot
◆ First silicon out
Yield learning & defect density reduction
Customer qualification & reliability testing
◆ Volume production release
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Site, permits & base build |  | 2026-08-02 | 2027-02-12 | 195 | 100%
1.1 | Site selection & seismic/vibration survey | Client | 2026-08-02 | 2026-09-15 | 45 | 100%
1.2 | Environmental permits & hazardous materials licence | Regulatory | 2026-09-01 | 2026-12-29 | 120 | 100%
1.3 | Fab basis of design & tool set freeze | Process | 2026-09-11 | 2026-11-04 | 55 | 100%
1.4 | Long-lead utility equipment procurement | Procurement | 2026-10-31 | 2027-03-19 | 140 | 90%
1.5 | Piling & vibration-isolated waffle slab | Civils | 2026-11-30 | 2027-02-12 | 75 | 100%
2 | Tool set frozen |  | 2026-11-05 | 2026-11-05 | — | —
3 | Permits granted |  | 2026-12-30 | 2026-12-30 | — | —
4 | Shell & cleanroom envelope |  | 2027-02-13 | 2027-09-10 | 210 | 45%
4.1 | Structural steel & building envelope | Structural | 2027-02-13 | 2027-05-13 | 90 | 90%
4.2 | Subfab & waffle slab penetrations | Civils | 2027-03-10 | 2027-05-08 | 60 | 70%
4.3 | Roof, weathertight & building dry-in | Structural | 2027-05-14 | 2027-06-17 | 35 | 20%
5 | Building dry-in complete |  | 2027-06-18 | 2027-06-18 | — | —
5.1 | Cleanroom wall & ceiling grid installation | Cleanroom | 2027-06-18 | 2027-08-26 | 70 | 0%
5.2 | Raised access floor & perforated tiles | Cleanroom | 2027-07-23 | 2027-09-05 | 45 | 0%
5.3 | Fan filter unit installation | Cleanroom | 2027-08-02 | 2027-09-20 | 50 | 0%
6 | Facility utilities & abatement |  | 2027-05-29 | 2027-12-04 | 190 | 10%
6.1 | Ultrapure water plant installation | Facilities | 2027-05-29 | 2027-08-26 | 90 | 30%
6.2 | UPW loop flush & resistivity | Facilities | 2027-08-27 | 2027-10-10 | 45 | 0%

## Slide 4
 | qualification |  |  |  |  | 
6.3 | Bulk & specialty gas yard construction | Facilities | 2027-06-18 | 2027-09-05 | 80 | 10%
6.4 | Gas distribution, VMB & leak testing | Facilities | 2027-09-06 | 2027-11-04 | 60 | 0%
6.5 | Exhaust, scrubber & abatement systems | Facilities | 2027-07-18 | 2027-10-10 | 85 | 0%
6.6 | Electrical substation & UPS energisation | Electrical | 2027-06-28 | 2027-09-25 | 90 | 0%
7 | Facility utilities available at hook-up points |  | 2027-11-15 | 2027-11-15 | — | —
8 | Cleanroom certification & protocol changeover |  | 2027-09-11 | 2028-01-08 | 120 | 0%
8.1 | Cleanroom construction protocol changeover | Cleanroom | 2027-09-11 | 2027-09-20 | 10 | 0%
8.2 | Gowning, airlocks & material entry procedures live | Cleanroom | 2027-09-21 | 2027-10-10 | 20 | 0%
8.3 | Air balancing & laminar flow verification | Cleanroom | 2027-10-06 | 2027-11-04 | 30 | 0%
8.4 | Particle count & ISO class certification | Cleanroom | 2027-11-05 | 2027-11-29 | 25 | 0%
8.5 | Vibration, EMI & acoustic survey | Commissioning | 2027-11-15 | 2027-12-04 | 20 | 0%
9 | Cleanroom certified to ISO class |  | 2027-12-05 | 2027-12-05 | — | —
10 | Tool move-in, hook-up & qualification |  | 2027-11-15 | 2028-06-06 | 205 | 0%
10.1 | Tool delivery sequence & rigging plan | Logistics | 2027-11-15 | 2027-12-09 | 25 | 0%
10.2 | Litho tool move-in & set | Tool install | 2027-12-10 | 2028-01-23 | 45 | 0%
10.3 | Etch & deposition tool move-in | Tool install | 2027-12-20 | 2028-02-12 | 55 | 0%
10.4 | Metrology & inspection tool move-in | Tool install | 2028-01-14 | 2028-02-22 | 40 | 0%
10.5 | Tool hook-up to gases, exhaust & UPW | Tool install | 2028-01-24 | 2028-04-02 | 70 | 0%
10.6 | Tool power-up & vendor installation qualification | Vendor | 2028-03-14 | 2028-05-02 | 50 | 0%
10.7 | Operational qualification & SPC baseline | Process | 2028-04-23 | 2028-06-06 | 45 | 0%
11 | Tool qualification complete |  | 2028-06-07 | 2028-06-07 | — | —

## Slide 5
12 | Process qualification & first silicon |  | 2028-03-24 | 2028-11-18 | 240 | 0%
12.1 | MES, automation & AMHS integration | IT | 2028-03-24 | 2028-05-22 | 60 | 0%
12.2 | Recipe loading & process module setup | Process | 2028-05-23 | 2028-06-26 | 35 | 0%
12.3 | First wafer through single module | Process | 2028-06-27 | 2028-07-06 | 10 | 0%
12.4 | Full process flow pilot lot | Process | 2028-07-07 | 2028-08-20 | 45 | 0%
13 | First silicon out |  | 2028-08-21 | 2028-08-21 | — | —
13.1 | Yield learning & defect density reduction | Process | 2028-08-21 | 2028-10-19 | 60 | 0%
13.2 | Customer qualification & reliability testing | Quality | 2028-10-05 | 2028-11-23 | 50 | 0%
14 | Volume production release |  | 2028-11-24 | 2028-11-24 | — | —