## Gantt
Semiconductor Fab Construction
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27 | Apr 3 | Apr 10 | Apr 17 | Apr 24 | May 1 | May 8 | May 15 | May 22 | May 29 | Jun 5 | Jun 12 | Jun 19 | Jun 26 | Jul 3 | Jul 10 | Jul 17 | Jul 24 | Jul 31 | Aug 7 | Aug 14 | Aug 21 | Aug 28 | Sep 4 | Sep 11 | Sep 18 | Sep 25 | Oct 2 | Oct 9 | Oct 16 | Oct 23 | Oct 30 | Nov 6 | Nov 13 | Nov 20 | Nov 27
1 | Site, permits & base build |  | 2026-08-02 | 2027-02-12 | 195
1.1 | Site selection & seismic/vibration survey | Client | 2026-08-02 | 2026-09-15 | 45
1.2 | Environmental permits & hazardous materials licence | Regulatory | 2026-09-01 | 2026-12-29 | 120
1.3 | Fab basis of design & tool set freeze | Process | 2026-09-11 | 2026-11-04 | 55
1.4 | Long-lead utility equipment procurement | Procurement | 2026-10-31 | 2027-03-19 | 140
1.5 | Piling & vibration-isolated waffle slab | Civils | 2026-11-30 | 2027-02-12 | 75
2 | ◆ Tool set frozen |  | 2026-11-05 | 2026-11-05 | [14 empty] | ◆
3 | ◆ Permits granted |  | 2026-12-30 | 2026-12-30 | [22 empty] | ◆
4 | Shell & cleanroom envelope |  | 2027-02-13 | 2027-09-10 | 210
4.1 | Structural steel & building envelope | Structural | 2027-02-13 | 2027-05-13 | 90
4.2 | Subfab & waffle slab penetrations | Civils | 2027-03-10 | 2027-05-08 | 60
4.3 | Roof, weathertight & building dry-in | Structural | 2027-05-14 | 2027-06-17 | 35
5 | ◆ Building dry-in complete |  | 2027-06-18 | 2027-06-18 | [46 empty] | ◆
5.1 | Cleanroom wall & ceiling grid installation | Cleanroom | 2027-06-18 | 2027-08-26 | 70
5.2 | Raised access floor & perforated tiles | Cleanroom | 2027-07-23 | 2027-09-05 | 45
5.3 | Fan filter unit installation | Cleanroom | 2027-08-02 | 2027-09-20 | 50
6 | Facility utilities & abatement |  | 2027-05-29 | 2027-12-04 | 190
6.1 | Ultrapure water plant installation | Facilities | 2027-05-29 | 2027-08-26 | 90
6.2 | UPW loop flush & resistivity qualification | Facilities | 2027-08-27 | 2027-10-10 | 45
6.3 | Bulk & specialty gas yard construction | Facilities | 2027-06-18 | 2027-09-05 | 80
6.4 | Gas distribution, VMB & leak testing | Facilities | 2027-09-06 | 2027-11-04 | 60
6.5 | Exhaust, scrubber & abatement systems | Facilities | 2027-07-18 | 2027-10-10 | 85
6.6 | Electrical substation & UPS energisation | Electrical | 2027-06-28 | 2027-09-25 | 90
7 | ◆ Facility utilities available at hook-up points |  | 2027-11-15 | 2027-11-15 | [68 empty] | ◆
8 | Cleanroom certification & protocol changeover |  | 2027-09-11 | 2028-01-08 | 120
8.1 | Cleanroom construction protocol changeover | Cleanroom | 2027-09-11 | 2027-09-20 | 10
8.2 | Gowning, airlocks & material entry procedures live | Cleanroom | 2027-09-21 | 2027-10-10 | 20
8.3 | Air balancing & laminar flow verification | Cleanroom | 2027-10-06 | 2027-11-04 | 30
8.4 | Particle count & ISO class certification | Cleanroom | 2027-11-05 | 2027-11-29 | 25
8.5 | Vibration, EMI & acoustic survey | Commissioning | 2027-11-15 | 2027-12-04 | 20
9 | ◆ Cleanroom certified to ISO class |  | 2027-12-05 | 2027-12-05 | [71 empty] | ◆
10 | Tool move-in, hook-up & qualification |  | 2027-11-15 | 2028-06-06 | 205
10.1 | Tool delivery sequence & rigging plan | Logistics | 2027-11-15 | 2027-12-09 | 25
10.2 | Litho tool move-in & set | Tool install | 2027-12-10 | 2028-01-23 | 45
10.3 | Etch & deposition tool move-in | Tool install | 2027-12-20 | 2028-02-12 | 55
10.4 | Metrology & inspection tool move-in | Tool install | 2028-01-14 | 2028-02-22 | 40
10.5 | Tool hook-up to gases, exhaust & UPW | Tool install | 2028-01-24 | 2028-04-02 | 70
10.6 | Tool power-up & vendor installation qualification | Vendor | 2028-03-14 | 2028-05-02 | 50
10.7 | Operational qualification & SPC baseline | Process | 2028-04-23 | 2028-06-06 | 45
11 | ◆ Tool qualification complete |  | 2028-06-07 | 2028-06-07 | [97 empty] | ◆
12 | Process qualification & first silicon |  | 2028-03-24 | 2028-11-18 | 240
12.1 | MES, automation & AMHS integration | IT | 2028-03-24 | 2028-05-22 | 60
12.2 | Recipe loading & process module setup | Process | 2028-05-23 | 2028-06-26 | 35
12.3 | First wafer through single module | Process | 2028-06-27 | 2028-07-06 | 10
12.4 | Full process flow pilot lot | Process | 2028-07-07 | 2028-08-20 | 45
13 | ◆ First silicon out |  | 2028-08-21 | 2028-08-21 | [108 empty] | ◆
13.1 | Yield learning & defect density reduction | Process | 2028-08-21 | 2028-10-19 | 60
13.2 | Customer qualification & reliability testing | Quality | 2028-10-05 | 2028-11-23 | 50
14 | ◆ Volume production release |  | 2028-11-24 | 2028-11-24 | [121 empty] | ◆