## Slide 1
Shipbuilding Project Schedule
Free Gantt chart template · gantts.app

## Slide 2
Shipbuilding Project Schedule
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Jun 5
Jun 19
Jul 3
Jul 17
Jul 31
Aug 14
Aug 28
Sep 11
Design & approval
Basic & detail design
Classification review
◆ Class approval
Procurement
Main engine & propulsion order
Steel & equipment orders
Steel work & blocks
◆ Steel cutting
Panel & sub-assembly
Block assembly & pre-outfitting
◆ Keel laying
Erection
Block erection & hull closure
Welding & alignment
Outfitting
Machinery & piping install
Electrical & accommodation
Painting & coatings
Launch, trials & delivery
◆ Launch / float-out
Quay-side commissioning
Sea trials
◆ Delivery
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Design & approval |  | 2026-08-02 | 2026-12-29 | 150 | 100%
1.1 | Basic & detail design | Design | 2026-08-02 | 2026-11-19 | 110 | 100%
1.2 | Classification review | Class | 2026-10-31 | 2026-12-29 | 60 | 90%
2 | Class approval |  | 2026-12-30 | 2026-12-30 | — | —
3 | Procurement |  | 2026-10-01 | 2027-06-17 | 260 | 60%
3.1 | Main engine & propulsion order | Procurement | 2026-10-01 | 2027-04-18 | 200 | 70%
3.2 | Steel & equipment orders | Procurement | 2026-11-30 | 2027-04-18 | 140 | 60%
4 | Steel work & blocks |  | 2026-12-30 | 2027-08-06 | 220 | 20%
5 | Steel cutting |  | 2027-01-04 | 2027-01-04 | — | —
5.1 | Panel & sub-assembly | Fabrication | 2027-01-04 | 2027-05-03 | 120 | 30%
5.2 | Block assembly & pre-outfitting | Fabrication | 2027-03-10 | 2027-08-06 | 150 | 10%
6 | Keel laying |  | 2027-04-09 | 2027-04-09 | — | —
7 | Erection |  | 2027-08-07 | 2027-12-24 | 140 | 0%
7.1 | Block erection & hull closure | Erection | 2027-08-07 | 2027-11-24 | 110 | 0%
7.2 | Welding & alignment | Erection | 2027-10-26 | 2027-12-24 | 60 | 0%
8 | Outfitting |  | 2027-11-15 | 2028-05-22 | 190 | 0%
8.1 | Machinery & piping install | Outfitting | 2027-11-15 | 2028-03-13 | 120 | 0%
8.2 | Electrical & accommodation | Outfitting | 2028-01-24 | 2028-05-02 | 100 | 0%
8.3 | Painting & coatings | Outfitting | 2028-03-24 | 2028-05-22 | 60 | 0%
9 | Launch, trials & delivery |  | 2028-05-23 | 2028-09-09 | 110 | 0%
10 | Launch / float-out |  | 2028-05-28 | 2028-05-28 | — | —

## Slide 4
10.1 | Quay-side commissioning | Commissioning | 2028-05-28 | 2028-07-21 | 55 | 0%
10.2 | Sea trials | Trials | 2028-07-27 | 2028-08-25 | 30 | 0%
11 | Delivery |  | 2028-09-10 | 2028-09-10 | — | —