## Gantt
Shipbuilding Project Schedule
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27 | Apr 3 | Apr 10 | Apr 17 | Apr 24 | May 1 | May 8 | May 15 | May 22 | May 29 | Jun 5 | Jun 12 | Jun 19 | Jun 26 | Jul 3 | Jul 10 | Jul 17 | Jul 24 | Jul 31 | Aug 7 | Aug 14 | Aug 21 | Aug 28 | Sep 4 | Sep 11
1 | Design & approval |  | 2026-08-02 | 2026-12-29 | 150
1.1 | Basic & detail design | Design | 2026-08-02 | 2026-11-19 | 110
1.2 | Classification review | Class | 2026-10-31 | 2026-12-29 | 60
2 | ◆ Class approval |  | 2026-12-30 | 2026-12-30 | [22 empty] | ◆
3 | Procurement |  | 2026-10-01 | 2027-06-17 | 260
3.1 | Main engine & propulsion order | Procurement | 2026-10-01 | 2027-04-18 | 200
3.2 | Steel & equipment orders | Procurement | 2026-11-30 | 2027-04-18 | 140
4 | Steel work & blocks |  | 2026-12-30 | 2027-08-06 | 220
5 | ◆ Steel cutting |  | 2027-01-04 | 2027-01-04 | [23 empty] | ◆
5.1 | Panel & sub-assembly | Fabrication | 2027-01-04 | 2027-05-03 | 120
5.2 | Block assembly & pre-outfitting | Fabrication | 2027-03-10 | 2027-08-06 | 150
6 | ◆ Keel laying |  | 2027-04-09 | 2027-04-09 | [36 empty] | ◆
7 | Erection |  | 2027-08-07 | 2027-12-24 | 140
7.1 | Block erection & hull closure | Erection | 2027-08-07 | 2027-11-24 | 110
7.2 | Welding & alignment | Erection | 2027-10-26 | 2027-12-24 | 60
8 | Outfitting |  | 2027-11-15 | 2028-05-22 | 190
8.1 | Machinery & piping install | Outfitting | 2027-11-15 | 2028-03-13 | 120
8.2 | Electrical & accommodation | Outfitting | 2028-01-24 | 2028-05-02 | 100
8.3 | Painting & coatings | Outfitting | 2028-03-24 | 2028-05-22 | 60
9 | Launch, trials & delivery |  | 2028-05-23 | 2028-09-09 | 110
10 | ◆ Launch / float-out |  | 2028-05-28 | 2028-05-28 | [96 empty] | ◆
10.1 | Quay-side commissioning | Commissioning | 2028-05-28 | 2028-07-21 | 55
10.2 | Sea trials | Trials | 2028-07-27 | 2028-08-25 | 30
11 | ◆ Delivery |  | 2028-09-10 | 2028-09-10 | [111 empty] | ◆