## Slide 1
SOC 2 Compliance Timeline
Free Gantt chart template · gantts.app

## Slide 2
SOC 2 Compliance Timeline
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Scoping & criteria
Define system boundary
Select trust services criteria
Choose auditor & engagement letter
Type I vs Type II decision
◆ Scope agreed
Control design
Risk assessment
Map controls to criteria
Policy set drafting
Control owners assigned
◆ Control matrix approved
Remediation
Access reviews & offboarding
Change management & review gates
Logging, alerting & monitoring
Vendor risk & DPA collection
Security awareness training
BCP & incident response test
◆ Remediation complete
Evidence & readiness
Evidence collection tooling
Populate evidence repository
Readiness assessment
Gap remediation from readiness
◆ Readiness sign-off
Type I report (optional)
Type I fieldwork
◆ Type I report issued
Observation window
◆ Observation period begins
Operate controls continuously
Monthly evidence checkpoints
Quarterly access review
◆ Observation period ends
Fieldwork & report
Auditor sample requests
Evidence submission
Auditor testing
Exceptions & management response
Draft report review
◆ Type II report issued
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Scoping & criteria |  | 2026-08-02 | 2026-09-10 | 40 | 100%
1.1 | Define system boundary | Security lead | 2026-08-02 | 2026-08-16 | 15 | 100%
1.2 | Select trust services criteria | Security lead | 2026-08-12 | 2026-08-26 | 15 | 100%
1.3 | Choose auditor & engagement letter | Management | 2026-08-17 | 2026-09-10 | 25 | 100%
1.4 | Type I vs Type II decision | Management | 2026-09-01 | 2026-09-10 | 10 | 100%
2 | Scope agreed |  | 2026-09-11 | 2026-09-11 | — | —
3 | Control design |  | 2026-09-11 | 2026-11-09 | 60 | 90%
3.1 | Risk assessment | Security lead | 2026-09-11 | 2026-10-05 | 25 | 100%
3.2 | Map controls to criteria | Security lead | 2026-09-26 | 2026-10-30 | 35 | 100%
3.3 | Policy set drafting | Compliance | 2026-10-01 | 2026-11-09 | 40 | 90%
3.4 | Control owners assigned | Management | 2026-10-26 | 2026-11-09 | 15 | 80%
4 | Control matrix approved |  | 2026-11-10 | 2026-11-10 | — | —
5 | Remediation |  | 2026-11-10 | 2027-02-02 | 85 | 40%
5.1 | Access reviews & offboarding | IT | 2026-11-10 | 2026-12-09 | 30 | 70%
5.2 | Change management & review gates | Engineering | 2026-11-15 | 2026-12-19 | 35 | 60%
5.3 | Logging, alerting & monitoring | Engineering | 2026-11-20 | 2027-01-03 | 45 | 40%
5.4 | Vendor risk & DPA collection | Compliance | 2026-11-30 | 2027-01-08 | 40 | 20%
5.5 | Security awareness training | HR | 2026-12-20 | 2027-01-08 | 20 | 0%
5.6 | BCP & incident response test | Security lead | 2026-12-30 | 2027-01-23 | 25 | 0%
6 | Remediation complete |  | 2027-02-03 | 2027-02-03 | — | —
7 | Evidence & readiness |  | 2026-12-30 | 2027-03-14 | 75 | 10%

## Slide 4
7.1 | Evidence collection tooling | Engineering | 2026-12-30 | 2027-01-28 | 30 | 30%
7.2 | Populate evidence repository | Compliance | 2027-01-19 | 2027-02-22 | 35 | 10%
7.3 | Readiness assessment | Auditor | 2027-02-08 | 2027-02-27 | 20 | 0%
7.4 | Gap remediation from readiness | Engineering | 2027-02-23 | 2027-03-14 | 20 | 0%
8 | Readiness sign-off |  | 2027-03-15 | 2027-03-15 | — | —
9 | Type I report (optional) |  | 2027-03-15 | 2027-04-08 | 25 | 0%
9.1 | Type I fieldwork | Auditor | 2027-03-15 | 2027-03-29 | 15 | 0%
10 | Type I report issued |  | 2027-04-09 | 2027-04-09 | — | —
11 | Observation window |  | 2027-03-15 | 2027-09-10 | 180 | 0%
12 | Observation period begins |  | 2027-03-15 | 2027-03-15 | — | —
12.1 | Operate controls continuously | All | 2027-03-15 | 2027-09-10 | 180 | 0%
12.2 | Monthly evidence checkpoints | Compliance | 2027-03-30 | 2027-09-10 | 165 | 0%
12.3 | Quarterly access review | IT | 2027-06-13 | 2027-06-22 | 10 | 0%
13 | Observation period ends |  | 2027-09-11 | 2027-09-11 | — | —
14 | Fieldwork & report |  | 2027-09-11 | 2027-11-24 | 75 | 0%
14.1 | Auditor sample requests | Auditor | 2027-09-11 | 2027-09-30 | 20 | 0%
14.2 | Evidence submission | Compliance | 2027-10-01 | 2027-10-25 | 25 | 0%
14.3 | Auditor testing | Auditor | 2027-10-06 | 2027-11-04 | 30 | 0%
14.4 | Exceptions & management response | Management | 2027-11-05 | 2027-11-19 | 15 | 0%
14.5 | Draft report review | Management | 2027-11-15 | 2027-11-24 | 10 | 0%
15 | Type II report issued |  | 2027-11-25 | 2027-11-25 | — | —