## Gantt
SOC 2 Compliance Timeline
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29
1 | Scoping & criteria |  | 2026-08-02 | 2026-09-10 | 40
1.1 | Define system boundary | Security lead | 2026-08-02 | 2026-08-16 | 15
1.2 | Select trust services criteria | Security lead | 2026-08-12 | 2026-08-26 | 15
1.3 | Choose auditor & engagement letter | Management | 2026-08-17 | 2026-09-10 | 25
1.4 | Type I vs Type II decision | Management | 2026-09-01 | 2026-09-10 | 10
2 | ◆ Scope agreed |  | 2026-09-11 | 2026-09-11 | [6 empty] | ◆
3 | Control design |  | 2026-09-11 | 2026-11-09 | 60
3.1 | Risk assessment | Security lead | 2026-09-11 | 2026-10-05 | 25
3.2 | Map controls to criteria | Security lead | 2026-09-26 | 2026-10-30 | 35
3.3 | Policy set drafting | Compliance | 2026-10-01 | 2026-11-09 | 40
3.4 | Control owners assigned | Management | 2026-10-26 | 2026-11-09 | 15
4 | ◆ Control matrix approved |  | 2026-11-10 | 2026-11-10 | [15 empty] | ◆
5 | Remediation |  | 2026-11-10 | 2027-02-02 | 85
5.1 | Access reviews & offboarding | IT | 2026-11-10 | 2026-12-09 | 30
5.2 | Change management & review gates | Engineering | 2026-11-15 | 2026-12-19 | 35
5.3 | Logging, alerting & monitoring | Engineering | 2026-11-20 | 2027-01-03 | 45
5.4 | Vendor risk & DPA collection | Compliance | 2026-11-30 | 2027-01-08 | 40
5.5 | Security awareness training | HR | 2026-12-20 | 2027-01-08 | 20
5.6 | BCP & incident response test | Security lead | 2026-12-30 | 2027-01-23 | 25
6 | ◆ Remediation complete |  | 2027-02-03 | 2027-02-03 | [27 empty] | ◆
7 | Evidence & readiness |  | 2026-12-30 | 2027-03-14 | 75
7.1 | Evidence collection tooling | Engineering | 2026-12-30 | 2027-01-28 | 30
7.2 | Populate evidence repository | Compliance | 2027-01-19 | 2027-02-22 | 35
7.3 | Readiness assessment | Auditor | 2027-02-08 | 2027-02-27 | 20
7.4 | Gap remediation from readiness | Engineering | 2027-02-23 | 2027-03-14 | 20
8 | ◆ Readiness sign-off |  | 2027-03-15 | 2027-03-15 | [33 empty] | ◆
9 | Type I report (optional) |  | 2027-03-15 | 2027-04-08 | 25
9.1 | Type I fieldwork | Auditor | 2027-03-15 | 2027-03-29 | 15
10 | ◆ Type I report issued |  | 2027-04-09 | 2027-04-09 | [36 empty] | ◆
11 | Observation window |  | 2027-03-15 | 2027-09-10 | 180
12 | ◆ Observation period begins |  | 2027-03-15 | 2027-03-15 | [33 empty] | ◆
12.1 | Operate controls continuously | All | 2027-03-15 | 2027-09-10 | 180
12.2 | Monthly evidence checkpoints | Compliance | 2027-03-30 | 2027-09-10 | 165
12.3 | Quarterly access review | IT | 2027-06-13 | 2027-06-22 | 10
13 | ◆ Observation period ends |  | 2027-09-11 | 2027-09-11 | [58 empty] | ◆
14 | Fieldwork & report |  | 2027-09-11 | 2027-11-24 | 75
14.1 | Auditor sample requests | Auditor | 2027-09-11 | 2027-09-30 | 20
14.2 | Evidence submission | Compliance | 2027-10-01 | 2027-10-25 | 25
14.3 | Auditor testing | Auditor | 2027-10-06 | 2027-11-04 | 30
14.4 | Exceptions & management response | Management | 2027-11-05 | 2027-11-19 | 15
14.5 | Draft report review | Management | 2027-11-15 | 2027-11-24 | 10
15 | ◆ Type II report issued |  | 2027-11-25 | 2027-11-25 | [69 empty] | ◆