## Slide 1
Software Development Plan
Free Gantt chart template · gantts.app

## Slide 2
Software Development Plan
Aug 3
Aug 17
Aug 31
Sep 14
Discovery
Requirements
Technical design
◆ Design approved
Development
Backend API
Frontend UI
Integration
QA & Testing
Test plan
Bug fixing
Launch
Deploy to production
◆ Go live
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Discovery |  | 2026-08-02 | 2026-08-11 | 10 | 100%
1.1 | Requirements | PM | 2026-08-02 | 2026-08-06 | 5 | 100%
1.2 | Technical design | Lead | 2026-08-07 | 2026-08-11 | 5 | 80%
1.3 | Design approved |  | 2026-08-12 | 2026-08-12 | — | —
2 | Development |  | 2026-08-12 | 2026-08-31 | 20 | 40%
2.1 | Backend API | Dev A | 2026-08-12 | 2026-08-29 | 18 | 60%
2.2 | Frontend UI | Dev B | 2026-08-12 | 2026-08-31 | 20 | 35%
2.3 | Integration | Team | 2026-09-01 | 2026-09-08 | 8 | 0%
3 | QA & Testing |  | 2026-09-09 | 2026-09-20 | 12 | 0%
3.1 | Test plan | QA | 2026-09-09 | 2026-09-12 | 4 | 0%
3.2 | Bug fixing | Team | 2026-09-13 | 2026-09-20 | 8 | 0%
4 | Launch |  | 2026-09-21 | 2026-09-23 | 3 | 0%
4.1 | Deploy to production | DevOps | 2026-09-21 | 2026-09-22 | 2 | 0%
4.2 | Go live |  | 2026-09-23 | 2026-09-23 | — | —