## Gantt
Solar Farm Construction Schedule
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17
1 | Development & feasibility |  | 2026-08-02 | 2026-09-15 | 45
1.1 | Site control & pre-feasibility | Development | 2026-08-02 | 2026-08-26 | 25
1.2 | Solar resource & layout | Engineering | 2026-08-22 | 2026-09-15 | 25
2 | Interconnection & environmental |  | 2026-09-11 | 2026-12-09 | 90
2.1 | Interconnection application & study | Development | 2026-09-11 | 2026-11-24 | 75
2.2 | Environmental assessment | Consultant | 2026-09-26 | 2026-11-14 | 50
3 | ◆ Interconnection agreement |  | 2026-12-10 | 2026-12-10 | [19 empty] | ◆
4 | Design & permitting |  | 2026-11-20 | 2027-01-18 | 60
4.1 | Civil & electrical design | Engineering | 2026-11-20 | 2026-12-29 | 40
4.2 | Local permits & approvals | Permitting | 2026-12-10 | 2027-01-18 | 40
5 | ◆ Notice to proceed |  | 2027-01-19 | 2027-01-19 | [25 empty] | ◆
6 | Procurement |  | 2026-12-20 | 2027-03-04 | 75
6.1 | Modules & inverters ordered | Procurement | 2026-12-20 | 2027-02-17 | 60
6.2 | Transformer & HV gear (long lead) | Procurement | 2026-12-20 | 2027-03-04 | 75
7 | Civil & mechanical |  | 2027-01-21 | 2027-04-05 | 75
7.1 | Mobilization & access roads | EPC | 2027-01-21 | 2027-02-04 | 15
7.2 | Grading & fencing | Civil | 2027-02-03 | 2027-02-22 | 20
7.3 | Pile driving & racking | Mechanical | 2027-02-20 | 2027-03-21 | 30
7.4 | Module install & DC wiring | Mechanical | 2027-03-15 | 2027-04-05 | 22
8 | Electrical & commissioning |  | 2027-03-30 | 2027-05-13 | 45
8.1 | Inverters, combiners & substation | Electrical | 2027-03-30 | 2027-04-23 | 25
8.2 | Testing & utility witness test | Commissioning | 2027-04-22 | 2027-05-05 | 14
9 | ◆ Commercial operation |  | 2027-05-14 | 2027-05-14 | [41 empty] | ◆