## Slide 1
Sprint Plan (2 weeks)
Free Gantt chart template · gantts.app

## Slide 2
Sprint Plan (2 weeks)
Aug 3
Sprint planning
Development
Story: build feature
Story: API work
Integration
QA & testing
◆ Sprint review
Retrospective
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Sprint planning | Team | 2026-08-02 | 2026-08-02 | 1 | 100%
2 | Development |  | 2026-08-03 | 2026-08-10 | 8 | 40%
2.1 | Story: build feature | Dev A | 2026-08-03 | 2026-08-07 | 5 | 60%
2.2 | Story: API work | Dev B | 2026-08-03 | 2026-08-08 | 6 | 40%
2.3 | Integration | Team | 2026-08-09 | 2026-08-10 | 2 | 0%
3 | QA & testing | QA | 2026-08-11 | 2026-08-12 | 2 | 0%
4 | Sprint review |  | 2026-08-13 | 2026-08-13 | — | —
5 | Retrospective | Team | 2026-08-13 | 2026-08-13 | 1 | 0%