## Slide 1
Stadium Construction
Free Gantt chart template · gantts.app

## Slide 2
Stadium Construction
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Jun 5
Design, consents & enabling works
Feasibility & capacity brief
◆ Opening fixture date fixed by league
Planning permission & safety certificate strategy
Concept & stadium bowl design
Detailed design & structural steel package
Site enabling, demolition & piling mat
Substructure & bowl
Piling & foundations
Basement & service tunnels
In-situ concrete frame
Precast terrace unit manufacture
Precast terrace erection
◆ Bowl structure complete
Roof & envelope
Roof steel fabrication
Compression ring erection
Cable net installation & tensioning
Roof lift weather window
Roof cladding & ETFE panels
◆ Facade & envelope watertight
Fit-out, hospitality & systems
Concourse & toilet block fit-out
Hospitality suites & boxes
Kitchens & catering outlets
Seat installation
Floodlighting & giant screens
Turnstiles, ticketing & access control
Broadcast, PA & scoreboard integration
Safety systems & control room commissioning
Pitch & playing surface
Pitch excavation & drainage
Undersoil heating & irrigation
Rootzone & growing medium placement
Hybrid turf stitching & laying
Grow-in & establishment period
◆ Pitch handed to grounds team
Test events, licensing & opening
Safety certificate application & inspection
Stewarding recruitment & training
Test event 1 - reduced capacity
Test event 2 - near full capacity
Snagging & final licensing conditions
◆ Safety certificate issued
◆ Opening fixture kick-off
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Design, consents & enabling works |  | 2026-08-02 | 2026-12-29 | 150 | 100%
1.1 | Feasibility & capacity brief | Client | 2026-08-02 | 2026-08-31 | 30 | 100%
2 | Opening fixture date fixed by league |  | 2026-09-01 | 2026-09-01 | — | —
2.1 | Planning permission & safety certificate strategy | Client | 2026-09-01 | 2026-11-19 | 80 | 100%
2.2 | Concept & stadium bowl design | Architect | 2026-09-01 | 2026-10-30 | 60 | 100%
2.3 | Detailed design & structural steel package | Engineer | 2026-10-31 | 2027-01-08 | 70 | 100%
2.4 | Site enabling, demolition & piling mat | Civils | 2026-11-20 | 2026-12-29 | 40 | 100%
3 | Substructure & bowl |  | 2026-12-30 | 2027-07-17 | 200 | 60%
3.1 | Piling & foundations | Civils | 2026-12-30 | 2027-02-27 | 60 | 100%
3.2 | Basement & service tunnels | Civils | 2027-02-28 | 2027-04-23 | 55 | 80%
3.3 | In-situ concrete frame | Contractor | 2027-02-28 | 2027-05-28 | 90 | 70%
3.4 | Precast terrace unit manufacture | Precaster | 2027-01-29 | 2027-04-28 | 90 | 90%
3.5 | Precast terrace erection | Contractor | 2027-05-09 | 2027-07-17 | 70 | 20%
4 | Bowl structure complete |  | 2027-07-18 | 2027-07-18 | — | —
5 | Roof & envelope |  | 2027-03-30 | 2027-12-24 | 270 | 10%
5.1 | Roof steel fabrication | Steelwork | 2027-03-30 | 2027-07-07 | 100 | 60%
5.2 | Compression ring erection | Steelwork | 2027-07-18 | 2027-09-05 | 50 | 0%
5.3 | Cable net installation & tensioning | Specialist | 2027-09-06 | 2027-10-20 | 45 | 0%
5.4 | Roof lift weather window | Specialist | 2027-10-21 | 2027-11-09 | 20 | 0%
5.5 | Roof cladding & ETFE panels | Cladding | 2027-11-10 | 2028-01-03 | 55 | 0%
6 | Facade & envelope |  | 2028-01-04 | 2028-01-04 | — | —

## Slide 4
 | watertight |  |  |  |  | 
7 | Fit-out, hospitality & systems |  | 2027-09-26 | 2028-04-02 | 190 | 0%
7.1 | Concourse & toilet block fit-out | Contractor | 2027-09-26 | 2027-12-04 | 70 | 0%
7.2 | Hospitality suites & boxes | Contractor | 2027-11-05 | 2028-01-18 | 75 | 0%
7.3 | Kitchens & catering outlets | Fit-out | 2027-12-05 | 2028-02-02 | 60 | 0%
7.4 | Seat installation | Contractor | 2028-01-04 | 2028-02-17 | 45 | 0%
7.5 | Floodlighting & giant screens | Systems | 2028-01-09 | 2028-02-22 | 45 | 0%
7.6 | Turnstiles, ticketing & access control | Systems | 2028-01-14 | 2028-03-03 | 50 | 0%
7.7 | Broadcast, PA & scoreboard integration | Systems | 2028-02-23 | 2028-04-07 | 45 | 0%
7.8 | Safety systems & control room commissioning | Safety | 2028-03-04 | 2028-04-12 | 40 | 0%
8 | Pitch & playing surface |  | 2027-11-15 | 2028-04-22 | 160 | 0%
8.1 | Pitch excavation & drainage | Pitch contractor | 2027-11-15 | 2027-12-19 | 35 | 0%
8.2 | Undersoil heating & irrigation | Pitch contractor | 2027-12-20 | 2028-01-18 | 30 | 0%
8.3 | Rootzone & growing medium placement | Pitch contractor | 2028-01-19 | 2028-02-12 | 25 | 0%
8.4 | Hybrid turf stitching & laying | Pitch contractor | 2028-02-13 | 2028-03-03 | 20 | 0%
8.5 | Grow-in & establishment period | Grounds | 2028-03-04 | 2028-04-22 | 50 | 0%
9 | Pitch handed to grounds team |  | 2028-04-23 | 2028-04-23 | — | —
10 | Test events, licensing & opening |  | 2028-04-13 | 2028-06-11 | 60 | 0%
10.1 | Safety certificate application & inspection | Client | 2028-04-13 | 2028-05-12 | 30 | 0%
10.2 | Stewarding recruitment & training | Ops | 2028-04-13 | 2028-05-22 | 40 | 0%
10.3 | Test event 1 - reduced capacity | Ops | 2028-04-25 | 2028-04-27 | 3 | 0%
10.4 | Test event 2 - near full capacity | Ops | 2028-05-08 | 2028-05-10 | 3 | 0%
10.5 | Snagging & final licensing conditions | Contractor | 2028-05-11 | 2028-06-01 | 22 | 0%
11 | Safety certificate issued |  | 2028-05-23 | 2028-05-23 | — | —

## Slide 5
12 | Opening fixture kick-off |  | 2028-06-12 | 2028-06-12 | — | —