## Gantt
Stadium Construction
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27 | Apr 3 | Apr 10 | Apr 17 | Apr 24 | May 1 | May 8 | May 15 | May 22 | May 29 | Jun 5 | Jun 12 | Jun 19
1 | Design, consents & enabling works |  | 2026-08-02 | 2026-12-29 | 150
1.1 | Feasibility & capacity brief | Client | 2026-08-02 | 2026-08-31 | 30
2 | ◆ Opening fixture date fixed by league |  | 2026-09-01 | 2026-09-01 | [5 empty] | ◆
2.1 | Planning permission & safety certificate strategy | Client | 2026-09-01 | 2026-11-19 | 80
2.2 | Concept & stadium bowl design | Architect | 2026-09-01 | 2026-10-30 | 60
2.3 | Detailed design & structural steel package | Engineer | 2026-10-31 | 2027-01-08 | 70
2.4 | Site enabling, demolition & piling mat | Civils | 2026-11-20 | 2026-12-29 | 40
3 | Substructure & bowl |  | 2026-12-30 | 2027-07-17 | 200
3.1 | Piling & foundations | Civils | 2026-12-30 | 2027-02-27 | 60
3.2 | Basement & service tunnels | Civils | 2027-02-28 | 2027-04-23 | 55
3.3 | In-situ concrete frame | Contractor | 2027-02-28 | 2027-05-28 | 90
3.4 | Precast terrace unit manufacture | Precaster | 2027-01-29 | 2027-04-28 | 90
3.5 | Precast terrace erection | Contractor | 2027-05-09 | 2027-07-17 | 70
4 | ◆ Bowl structure complete |  | 2027-07-18 | 2027-07-18 | [51 empty] | ◆
5 | Roof & envelope |  | 2027-03-30 | 2027-12-24 | 270
5.1 | Roof steel fabrication | Steelwork | 2027-03-30 | 2027-07-07 | 100
5.2 | Compression ring erection | Steelwork | 2027-07-18 | 2027-09-05 | 50
5.3 | Cable net installation & tensioning | Specialist | 2027-09-06 | 2027-10-20 | 45
5.4 | Roof lift weather window | Specialist | 2027-10-21 | 2027-11-09 | 20
5.5 | Roof cladding & ETFE panels | Cladding | 2027-11-10 | 2028-01-03 | 55
6 | ◆ Facade & envelope watertight |  | 2028-01-04 | 2028-01-04 | [75 empty] | ◆
7 | Fit-out, hospitality & systems |  | 2027-09-26 | 2028-04-02 | 190
7.1 | Concourse & toilet block fit-out | Contractor | 2027-09-26 | 2027-12-04 | 70
7.2 | Hospitality suites & boxes | Contractor | 2027-11-05 | 2028-01-18 | 75
7.3 | Kitchens & catering outlets | Fit-out | 2027-12-05 | 2028-02-02 | 60
7.4 | Seat installation | Contractor | 2028-01-04 | 2028-02-17 | 45
7.5 | Floodlighting & giant screens | Systems | 2028-01-09 | 2028-02-22 | 45
7.6 | Turnstiles, ticketing & access control | Systems | 2028-01-14 | 2028-03-03 | 50
7.7 | Broadcast, PA & scoreboard integration | Systems | 2028-02-23 | 2028-04-07 | 45
7.8 | Safety systems & control room commissioning | Safety | 2028-03-04 | 2028-04-12 | 40
8 | Pitch & playing surface |  | 2027-11-15 | 2028-04-22 | 160
8.1 | Pitch excavation & drainage | Pitch contractor | 2027-11-15 | 2027-12-19 | 35
8.2 | Undersoil heating & irrigation | Pitch contractor | 2027-12-20 | 2028-01-18 | 30
8.3 | Rootzone & growing medium placement | Pitch contractor | 2028-01-19 | 2028-02-12 | 25
8.4 | Hybrid turf stitching & laying | Pitch contractor | 2028-02-13 | 2028-03-03 | 20
8.5 | Grow-in & establishment period | Grounds | 2028-03-04 | 2028-04-22 | 50
9 | ◆ Pitch handed to grounds team |  | 2028-04-23 | 2028-04-23 | [91 empty] | ◆
10 | Test events, licensing & opening |  | 2028-04-13 | 2028-06-11 | 60
10.1 | Safety certificate application & inspection | Client | 2028-04-13 | 2028-05-12 | 30
10.2 | Stewarding recruitment & training | Ops | 2028-04-13 | 2028-05-22 | 40
10.3 | Test event 1 - reduced capacity | Ops | 2028-04-25 | 2028-04-27 | 3
10.4 | Test event 2 - near full capacity | Ops | 2028-05-08 | 2028-05-10 | 3
10.5 | Snagging & final licensing conditions | Contractor | 2028-05-11 | 2028-06-01 | 22
11 | ◆ Safety certificate issued |  | 2028-05-23 | 2028-05-23 | [95 empty] | ◆
12 | ◆ Opening fixture kick-off |  | 2028-06-12 | 2028-06-12 | [98 empty] | ◆