## Slide 1
Study Plan
Free Gantt chart template · gantts.app

## Slide 2
Study Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Plan & set up
List subjects & topics
Gather materials & resources
Assess strengths & gaps
Set exam dates & goals
◆ Study plan ready
Learn, first pass
Work through core topics
Make notes & flashcards
Weekly review & catch-up
◆ First pass complete
Practice & active recall
Practice questions by topic
Spaced repetition (flashcards)
First timed past paper
◆ Practice underway
Revise weak areas
Identify & review weak topics
Condense to summary sheets
◆ Weak areas consolidated
Mock exams & final review
Full timed mock exams
Review mock results
Final summaries & rest
◆ Ready for exams
Exam week
Exam logistics (venue, materials)
Sit exams
◆ Exams complete
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Plan & set up |  | 2026-08-02 | 2026-08-08 | 7 | 100%
1.1 | List subjects & topics | Student | 2026-08-02 | 2026-08-03 | 2 | 100%
1.2 | Gather materials & resources | Student | 2026-08-03 | 2026-08-05 | 3 | 100%
1.3 | Assess strengths & gaps | Student | 2026-08-05 | 2026-08-06 | 2 | 100%
1.4 | Set exam dates & goals | Student | 2026-08-06 | 2026-08-08 | 3 | 100%
2 | Study plan ready |  | 2026-08-09 | 2026-08-09 | , | ,
3 | Learn, first pass |  | 2026-08-09 | 2026-08-29 | 21 | 40%
3.1 | Work through core topics | Student | 2026-08-09 | 2026-08-26 | 18 | 50%
3.2 | Make notes & flashcards | Student | 2026-08-11 | 2026-08-26 | 16 | 40%
3.3 | Weekly review & catch-up | Student | 2026-08-16 | 2026-08-29 | 14 | 20%
4 | First pass complete |  | 2026-08-30 | 2026-08-30 | , | ,
5 | Practice & active recall |  | 2026-08-23 | 2026-09-12 | 21 | 0%
5.1 | Practice questions by topic | Student | 2026-08-23 | 2026-09-09 | 18 | 0%
5.2 | Spaced repetition (flashcards) | Student | 2026-08-23 | 2026-09-12 | 21 | 0%
5.3 | First timed past paper | Student | 2026-09-01 | 2026-09-02 | 2 | 0%
6 | Practice underway |  | 2026-09-13 | 2026-09-13 | , | ,
7 | Revise weak areas |  | 2026-09-06 | 2026-09-19 | 14 | 0%
7.1 | Identify & review weak topics | Student | 2026-09-06 | 2026-09-14 | 9 | 0%
7.2 | Condense to summary sheets | Student | 2026-09-11 | 2026-09-16 | 6 | 0%
8 | Weak areas consolidated |  | 2026-09-20 | 2026-09-20 | , | ,
9 | Mock exams & final review |  | 2026-09-16 | 2026-09-27 | 12 | 0%

## Slide 4
9.1 | Full timed mock exams | Student | 2026-09-16 | 2026-09-23 | 8 | 0%
9.2 | Review mock results | Student | 2026-09-22 | 2026-09-24 | 3 | 0%
9.3 | Final summaries & rest | Student | 2026-09-25 | 2026-09-27 | 3 | 0%
10 | Ready for exams |  | 2026-09-28 | 2026-09-28 | , | ,
11 | Exam week |  | 2026-09-28 | 2026-10-04 | 7 | 0%
11.1 | Exam logistics (venue, materials) | Student | 2026-09-28 | 2026-09-28 | 1 | 0%
11.2 | Sit exams | Student | 2026-09-29 | 2026-10-04 | 6 | 0%
12 | Exams complete |  | 2026-10-05 | 2026-10-05 | , | ,