## Gantt
Study Plan
Made free at gantts.app, edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12
1 | Plan & set up |  | 2026-08-02 | 2026-08-08 | 7
1.1 | List subjects & topics | Student | 2026-08-02 | 2026-08-03 | 2
1.2 | Gather materials & resources | Student | 2026-08-03 | 2026-08-05 | 3
1.3 | Assess strengths & gaps | Student | 2026-08-05 | 2026-08-06 | 2
1.4 | Set exam dates & goals | Student | 2026-08-06 | 2026-08-08 | 3
2 | ◆ Study plan ready |  | 2026-08-09 | 2026-08-09 |  |  | ◆
3 | Learn, first pass |  | 2026-08-09 | 2026-08-29 | 21
3.1 | Work through core topics | Student | 2026-08-09 | 2026-08-26 | 18
3.2 | Make notes & flashcards | Student | 2026-08-11 | 2026-08-26 | 16
3.3 | Weekly review & catch-up | Student | 2026-08-16 | 2026-08-29 | 14
4 | ◆ First pass complete |  | 2026-08-30 | 2026-08-30 | [5 empty] | ◆
5 | Practice & active recall |  | 2026-08-23 | 2026-09-12 | 21
5.1 | Practice questions by topic | Student | 2026-08-23 | 2026-09-09 | 18
5.2 | Spaced repetition (flashcards) | Student | 2026-08-23 | 2026-09-12 | 21
5.3 | First timed past paper | Student | 2026-09-01 | 2026-09-02 | 2
6 | ◆ Practice underway |  | 2026-09-13 | 2026-09-13 | [7 empty] | ◆
7 | Revise weak areas |  | 2026-09-06 | 2026-09-19 | 14
7.1 | Identify & review weak topics | Student | 2026-09-06 | 2026-09-14 | 9
7.2 | Condense to summary sheets | Student | 2026-09-11 | 2026-09-16 | 6
8 | ◆ Weak areas consolidated |  | 2026-09-20 | 2026-09-20 | [8 empty] | ◆
9 | Mock exams & final review |  | 2026-09-16 | 2026-09-27 | 12
9.1 | Full timed mock exams | Student | 2026-09-16 | 2026-09-23 | 8
9.2 | Review mock results | Student | 2026-09-22 | 2026-09-24 | 3
9.3 | Final summaries & rest | Student | 2026-09-25 | 2026-09-27 | 3
10 | ◆ Ready for exams |  | 2026-09-28 | 2026-09-28 | [9 empty] | ◆
11 | Exam week |  | 2026-09-28 | 2026-10-04 | 7
11.1 | Exam logistics (venue, materials) | Student | 2026-09-28 | 2026-09-28 | 1
11.2 | Sit exams | Student | 2026-09-29 | 2026-10-04 | 6
12 | ◆ Exams complete |  | 2026-10-05 | 2026-10-05 | [10 empty] | ◆