## Slide 1
Trade Show Planning Timeline
Free Gantt chart template · gantts.app

## Slide 2
Trade Show Planning Timeline
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
Space selection & contract
Show selection & objectives
Budget approval
Floor plan review & space selection
◆ Space contracted
Stand design & build
Stand brief & concept design
Contractor selection
Design approval by show management
Graphics & content production
Stand fabrication
Pre-build & sign-off
Show services & logistics
Exhibitor manual review
Advance-rate service orders
◆ Advance order deadline
Freight booking & customs docs
Stand & product shipping
◆ Shipping deadline
Pre-show marketing
Target account list
Invitation campaign
Meeting booking
Press & speaker slots
Social & website countdown
Staffing & training
Stand rota & role assignment
Travel & accommodation booking
Product & messaging briefing
Demo dry-run & lead capture training
Show days
Build-up
◆ Show opens
Meetings, demos & floor coverage
Daily lead review
Breakdown & outbound freight
Lead follow-up & review
Lead upload & qualification
Tiered follow-up campaign
Pipeline attribution & cost review
◆ Next-show decision
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Space selection & contract |  | 2026-08-02 | 2026-09-25 | 55 | 100%
1.1 | Show selection & objectives | Marketing | 2026-08-02 | 2026-08-21 | 20 | 100%
1.2 | Budget approval | Marketing | 2026-08-17 | 2026-09-05 | 20 | 100%
1.3 | Floor plan review & space selection | Marketing | 2026-09-01 | 2026-09-25 | 25 | 100%
2 | Space contracted |  | 2026-09-26 | 2026-09-26 | — | —
3 | Stand design & build |  | 2026-09-26 | 2027-02-02 | 130 | 60%
3.1 | Stand brief & concept design | Design | 2026-09-26 | 2026-10-30 | 35 | 100%
3.2 | Contractor selection | Marketing | 2026-10-21 | 2026-11-19 | 30 | 100%
3.3 | Design approval by show management | Contractor | 2026-11-20 | 2026-12-14 | 25 | 60%
3.4 | Graphics & content production | Design | 2026-11-30 | 2027-01-08 | 40 | 40%
3.5 | Stand fabrication | Contractor | 2026-12-15 | 2027-01-28 | 45 | 20%
3.6 | Pre-build & sign-off | Contractor | 2027-01-24 | 2027-02-02 | 10 | 0%
4 | Show services & logistics |  | 2026-10-31 | 2027-02-17 | 110 | 40%
4.1 | Exhibitor manual review | Ops | 2026-10-31 | 2026-11-14 | 15 | 100%
4.2 | Advance-rate service orders | Ops | 2026-11-15 | 2026-12-09 | 25 | 60%
5 | Advance order deadline |  | 2026-12-10 | 2026-12-10 | — | —
5.1 | Freight booking & customs docs | Logistics | 2026-12-20 | 2027-01-13 | 25 | 20%
5.2 | Stand & product shipping | Logistics | 2027-02-03 | 2027-02-14 | 12 | 0%
6 | Shipping deadline |  | 2027-02-15 | 2027-02-15 | — | —
7 | Pre-show marketing |  | 2026-11-20 | 2027-03-04 | 105 | 30%
7.1 | Target account list | Marketing | 2026-11-20 | 2026-12-09 | 20 | 100%

## Slide 4
7.2 | Invitation campaign | Marketing | 2026-12-15 | 2027-01-28 | 45 | 40%
7.3 | Meeting booking | Sales | 2027-01-04 | 2027-02-27 | 55 | 20%
7.4 | Press & speaker slots | Comms | 2026-11-30 | 2027-01-28 | 60 | 50%
7.5 | Social & website countdown | Marketing | 2027-02-03 | 2027-03-04 | 30 | 0%
8 | Staffing & training |  | 2026-12-20 | 2027-03-04 | 75 | 20%
8.1 | Stand rota & role assignment | Sales | 2026-12-20 | 2027-01-13 | 25 | 60%
8.2 | Travel & accommodation booking | Ops | 2026-12-30 | 2027-01-23 | 25 | 40%
8.3 | Product & messaging briefing | Product | 2027-02-08 | 2027-02-22 | 15 | 0%
8.4 | Demo dry-run & lead capture training | Sales | 2027-02-23 | 2027-03-04 | 10 | 0%
9 | Show days |  | 2027-03-05 | 2027-03-16 | 12 | 0%
9.1 | Build-up | Contractor | 2027-03-05 | 2027-03-07 | 3 | 0%
10 | Show opens |  | 2027-03-08 | 2027-03-08 | — | —
10.1 | Meetings, demos & floor coverage | Stand team | 2027-03-08 | 2027-03-11 | 4 | 0%
10.2 | Daily lead review | Marketing | 2027-03-08 | 2027-03-11 | 4 | 0%
10.3 | Breakdown & outbound freight | Logistics | 2027-03-12 | 2027-03-16 | 5 | 0%
11 | Lead follow-up & review |  | 2027-03-12 | 2027-05-15 | 65 | 0%
11.1 | Lead upload & qualification | Marketing | 2027-03-12 | 2027-03-16 | 5 | 0%
11.2 | Tiered follow-up campaign | Sales | 2027-03-16 | 2027-04-14 | 30 | 0%
11.3 | Pipeline attribution & cost review | Marketing | 2027-04-14 | 2027-05-08 | 25 | 0%
12 | Next-show decision |  | 2027-05-16 | 2027-05-16 | — | —