## Slide 1
Training Program Rollout
Free Gantt chart template · gantts.app

## Slide 2
Training Program Rollout
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Needs analysis
Training needs assessment
Define audience & objectives
Skills-gap analysis
◆ Needs signed off
Design
Learning objectives & outcomes
Curriculum & modality design
Assessment & success metrics
◆ Design approved
Development
Build content & materials
LMS setup & upload
Facilitator guides & train-the-trainer
◆ Content ready
Pilot
Run pilot cohort
Gather feedback & evaluate
Revise materials
◆ Pilot signed off
Rollout
Schedule cohorts & comms
Enroll & communicate
Deliver training waves
◆ Rollout complete
Evaluate & sustain
Measure results (Kirkpatrick)
Reinforcement & job aids
Program review & iterate
◆ 90-day review
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Needs analysis |  | 2026-08-02 | 2026-08-19 | 18 | 100%
1.1 | Training needs assessment | L&D | 2026-08-02 | 2026-08-09 | 8 | 100%
1.2 | Define audience & objectives | L&D | 2026-08-10 | 2026-08-15 | 6 | 100%
1.3 | Skills-gap analysis | L&D | 2026-08-12 | 2026-08-19 | 8 | 80%
2 | Needs signed off |  | 2026-08-20 | 2026-08-20 | , | ,
3 | Design |  | 2026-08-20 | 2026-09-08 | 20 | 40%
3.1 | Learning objectives & outcomes | Instructional Designer | 2026-08-20 | 2026-08-26 | 7 | 60%
3.2 | Curriculum & modality design | Instructional Designer | 2026-08-27 | 2026-09-05 | 10 | 20%
3.3 | Assessment & success metrics | L&D | 2026-08-30 | 2026-09-06 | 8 | 0%
4 | Design approved |  | 2026-09-09 | 2026-09-09 | , | ,
5 | Development |  | 2026-09-06 | 2026-10-05 | 30 | 0%
5.1 | Build content & materials | Instructional Designer | 2026-09-06 | 2026-09-25 | 20 | 0%
5.2 | LMS setup & upload | L&D Ops | 2026-09-19 | 2026-09-30 | 12 | 0%
5.3 | Facilitator guides & train-the-trainer | L&D | 2026-09-26 | 2026-10-05 | 10 | 0%
6 | Content ready |  | 2026-10-06 | 2026-10-06 | , | ,
7 | Pilot |  | 2026-10-06 | 2026-10-23 | 18 | 0%
7.1 | Run pilot cohort | Facilitator | 2026-10-06 | 2026-10-15 | 10 | 0%
7.2 | Gather feedback & evaluate | L&D | 2026-10-13 | 2026-10-19 | 7 | 0%
7.3 | Revise materials | Instructional Designer | 2026-10-19 | 2026-10-23 | 5 | 0%
8 | Pilot signed off |  | 2026-10-24 | 2026-10-24 | , | ,
9 | Rollout |  | 2026-10-24 | 2026-11-22 | 30 | 0%

## Slide 4
9.1 | Schedule cohorts & comms | L&D Ops | 2026-10-24 | 2026-11-02 | 10 | 0%
9.2 | Enroll & communicate | L&D | 2026-10-31 | 2026-11-07 | 8 | 0%
9.3 | Deliver training waves | Facilitator | 2026-11-05 | 2026-11-22 | 18 | 0%
10 | Rollout complete |  | 2026-11-23 | 2026-11-23 | , | ,
11 | Evaluate & sustain |  | 2026-11-15 | 2026-12-06 | 22 | 0%
11.1 | Measure results (Kirkpatrick) | L&D | 2026-11-15 | 2026-11-24 | 10 | 0%
11.2 | Reinforcement & job aids | L&D | 2026-11-20 | 2026-11-29 | 10 | 0%
11.3 | Program review & iterate | L&D | 2026-11-27 | 2026-12-04 | 8 | 0%
12 | 90-day review |  | 2026-12-07 | 2026-12-07 | , | ,