## Gantt
Training Program Rollout
Made free at gantts.app, edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14
1 | Needs analysis |  | 2026-08-02 | 2026-08-19 | 18
1.1 | Training needs assessment | L&D | 2026-08-02 | 2026-08-09 | 8
1.2 | Define audience & objectives | L&D | 2026-08-10 | 2026-08-15 | 6
1.3 | Skills-gap analysis | L&D | 2026-08-12 | 2026-08-19 | 8
2 | ◆ Needs signed off |  | 2026-08-20 | 2026-08-20 |  |  |  | ◆
3 | Design |  | 2026-08-20 | 2026-09-08 | 20
3.1 | Learning objectives & outcomes | Instructional Designer | 2026-08-20 | 2026-08-26 | 7
3.2 | Curriculum & modality design | Instructional Designer | 2026-08-27 | 2026-09-05 | 10
3.3 | Assessment & success metrics | L&D | 2026-08-30 | 2026-09-06 | 8
4 | ◆ Design approved |  | 2026-09-09 | 2026-09-09 | [6 empty] | ◆
5 | Development |  | 2026-09-06 | 2026-10-05 | 30
5.1 | Build content & materials | Instructional Designer | 2026-09-06 | 2026-09-25 | 20
5.2 | LMS setup & upload | L&D Ops | 2026-09-19 | 2026-09-30 | 12
5.3 | Facilitator guides & train-the-trainer | L&D | 2026-09-26 | 2026-10-05 | 10
6 | ◆ Content ready |  | 2026-10-06 | 2026-10-06 | [10 empty] | ◆
7 | Pilot |  | 2026-10-06 | 2026-10-23 | 18
7.1 | Run pilot cohort | Facilitator | 2026-10-06 | 2026-10-15 | 10
7.2 | Gather feedback & evaluate | L&D | 2026-10-13 | 2026-10-19 | 7
7.3 | Revise materials | Instructional Designer | 2026-10-19 | 2026-10-23 | 5
8 | ◆ Pilot signed off |  | 2026-10-24 | 2026-10-24 | [12 empty] | ◆
9 | Rollout |  | 2026-10-24 | 2026-11-22 | 30
9.1 | Schedule cohorts & comms | L&D Ops | 2026-10-24 | 2026-11-02 | 10
9.2 | Enroll & communicate | L&D | 2026-10-31 | 2026-11-07 | 8
9.3 | Deliver training waves | Facilitator | 2026-11-05 | 2026-11-22 | 18
10 | ◆ Rollout complete |  | 2026-11-23 | 2026-11-23 | [17 empty] | ◆
11 | Evaluate & sustain |  | 2026-11-15 | 2026-12-06 | 22
11.1 | Measure results (Kirkpatrick) | L&D | 2026-11-15 | 2026-11-24 | 10
11.2 | Reinforcement & job aids | L&D | 2026-11-20 | 2026-11-29 | 10
11.3 | Program review & iterate | L&D | 2026-11-27 | 2026-12-04 | 8
12 | ◆ 90-day review |  | 2026-12-07 | 2026-12-07 | [19 empty] | ◆