## Slide 1
Tunnel Construction
Free Gantt chart template · gantts.app

## Slide 2
Tunnel Construction
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Jun 5
Jun 19
Jul 3
Jul 17
Jul 31
Aug 14
Aug 28
Sep 11
Sep 25
Oct 9
Oct 23
Nov 6
Nov 20
Dec 4
Dec 18
Jan 1
Jan 15
Jan 29
Feb 12
Feb 26
Mar 12
Mar 26
Apr 9
Apr 23
May 7
Consents, ground investigation & procurement
Ground investigation & borehole programme
Geotechnical baseline report
Alignment & tunnel lining design
Planning consent & statutory order
TBM specification & tender
◆ TBM contract awarded
◆ Consents granted
Launch shaft & site establishment
Site establishment & compound
Shaft diaphragm walls
Shaft excavation & base slab
Launch chamber & thrust wall
Segment production run — first 1,000 rings
◆ Launch shaft ready to receive TBM
TBM manufacture, delivery & assembly
TBM detailed design & cutterhead configuration
TBM manufacture
Factory acceptance test
TBM shipping & road transport to site
TBM lowering & underground assembly
◆ TBM ready to launch
Tunnel drive
TBM launch through the soft eye
Learning-curve drive — first 200 m
Muck removal & spoil haulage system live
Segment supply & ring delivery logistics
Settlement monitoring & compensation grouting
Sustained drive through mixed ground
Hyperbaric intervention & cutter tool change
Drive beneath river crossing
Final drive to reception shaft
◆ Breakthrough at reception shaft
Cross-passages & secondary works
Cross-passage ground treatment
Cross-passage excavation & lining
Annulus grouting & ring survey
TBM disassembly & removal
Secondary lining & invert concrete
◆ Tunnel structurally complete
Fit-out, systems & commissioning
Walkway, drainage & cable containment
Ventilation fans & ductwork installation
Fire main, hydrants & suppression system
Power distribution & tunnel lighting
Comms, SCADA & CCTV installation
Hot smoke test & fire drill with emergency services
Safety case & regulator approval
◆ Tunnel handed over for operation
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Consents, ground investigation & procurement |  | 2026-08-02 | 2027-01-18 | 170 | 100%
1.1 | Ground investigation & borehole programme | Geotech | 2026-08-02 | 2026-09-25 | 55 | 100%
1.2 | Geotechnical baseline report | Geotech | 2026-09-21 | 2026-10-20 | 30 | 100%
1.3 | Alignment & tunnel lining design | Designer | 2026-10-01 | 2026-11-29 | 60 | 100%
1.4 | Planning consent & statutory order | Client | 2026-08-22 | 2027-01-08 | 140 | 100%
1.5 | TBM specification & tender | Procurement | 2026-11-10 | 2026-12-24 | 45 | 100%
2 | TBM contract awarded |  | 2026-12-30 | 2026-12-30 | — | —
3 | Consents granted |  | 2027-01-09 | 2027-01-09 | — | —
4 | Launch shaft & site establishment |  | 2026-12-30 | 2027-07-17 | 200 | 65%
4.1 | Site establishment & compound | Civils | 2026-12-30 | 2027-02-02 | 35 | 100%
4.2 | Shaft diaphragm walls | Civils | 2027-02-18 | 2027-04-18 | 60 | 100%
4.3 | Shaft excavation & base slab | Civils | 2027-04-14 | 2027-06-22 | 70 | 80%
4.4 | Launch chamber & thrust wall | Civils | 2027-06-13 | 2027-07-17 | 35 | 40%
4.5 | Segment production run — first 1,000 rings | Casting yard | 2027-04-09 | 2027-08-06 | 120 | 50%
5 | Launch shaft ready to receive TBM |  | 2027-07-18 | 2027-07-18 | — | —
6 | TBM manufacture, delivery & assembly |  | 2026-12-30 | 2027-11-14 | 320 | 40%
6.1 | TBM detailed design & cutterhead configuration | TBM supplier | 2026-12-30 | 2027-02-27 | 60 | 100%
6.2 | TBM manufacture | TBM supplier | 2027-02-28 | 2027-07-27 | 150 | 60%
6.3 | Factory acceptance test | TBM supplier | 2027-07-28 | 2027-08-16 | 20 | 0%
6.4 | TBM shipping & road transport to site | Logistics | 2027-08-17 | 2027-09-15 | 30 | 0%
6.5 | TBM lowering & | TBM crew | 2027-09-16 | 2027-10-30 | 45 | 0%

## Slide 4
 | underground assembly |  |  |  |  | 
7 | TBM ready to launch |  | 2027-11-15 | 2027-11-15 | — | —
8 | Tunnel drive |  | 2027-11-15 | 2028-09-09 | 300 | 0%
8.1 | TBM launch through the soft eye | TBM crew | 2027-11-15 | 2027-12-04 | 20 | 0%
8.2 | Learning-curve drive — first 200 m | TBM crew | 2027-12-05 | 2028-01-08 | 35 | 0%
8.3 | Muck removal & spoil haulage system live | Logistics | 2027-11-15 | 2028-09-09 | 300 | 0%
8.4 | Segment supply & ring delivery logistics | Casting yard | 2027-11-15 | 2028-09-09 | 300 | 0%
8.5 | Settlement monitoring & compensation grouting | Instrumentation | 2027-12-05 | 2028-09-09 | 280 | 0%
8.6 | Sustained drive through mixed ground | TBM crew | 2028-01-09 | 2028-04-27 | 110 | 0%
8.7 | Hyperbaric intervention & cutter tool change | TBM crew | 2028-04-28 | 2028-05-12 | 15 | 0%
8.8 | Drive beneath river crossing | TBM crew | 2028-05-13 | 2028-06-26 | 45 | 0%
8.9 | Final drive to reception shaft | TBM crew | 2028-06-27 | 2028-08-25 | 60 | 0%
9 | Breakthrough at reception shaft |  | 2028-08-26 | 2028-08-26 | — | —
10 | Cross-passages & secondary works |  | 2028-03-24 | 2028-12-08 | 260 | 0%
10.1 | Cross-passage ground treatment | Ground eng | 2028-03-24 | 2028-05-17 | 55 | 0%
10.2 | Cross-passage excavation & lining | Mining crew | 2028-05-18 | 2028-08-15 | 90 | 0%
10.3 | Annulus grouting & ring survey | TBM crew | 2028-07-02 | 2028-08-30 | 60 | 0%
10.4 | TBM disassembly & removal | TBM crew | 2028-08-26 | 2028-09-29 | 35 | 0%
10.5 | Secondary lining & invert concrete | Civils | 2028-09-30 | 2028-12-08 | 70 | 0%
11 | Tunnel structurally complete |  | 2028-12-09 | 2028-12-09 | — | —
12 | Fit-out, systems & commissioning |  | 2028-10-30 | 2029-05-12 | 195 | 0%
12.1 | Walkway, drainage & cable containment | Fit-out | 2028-10-30 | 2028-12-23 | 55 | 0%
12.2 | Ventilation fans & ductwork installation | Mechanical | 2028-12-09 | 2029-01-27 | 50 | 0%
12.3 | Fire main, hydrants & suppression system | Mechanical | 2028-12-24 | 2029-02-06 | 45 | 0%
12.4 | Power distribution & | Electrical | 2028-12-29 | 2029-02-16 | 50 | 0%

## Slide 5
 | tunnel lighting |  |  |  |  | 
12.5 | Comms, SCADA & CCTV installation | Systems | 2029-01-28 | 2029-03-08 | 40 | 0%
12.6 | Hot smoke test & fire drill with emergency services | Commissioning | 2029-03-29 | 2029-04-12 | 15 | 0%
12.7 | Safety case & regulator approval | Client | 2029-04-13 | 2029-05-12 | 30 | 0%
13 | Tunnel handed over for operation |  | 2029-05-13 | 2029-05-13 | — | —