## Gantt
Tunnel Construction
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27 | Apr 3 | Apr 10 | Apr 17 | Apr 24 | May 1 | May 8 | May 15 | May 22 | May 29 | Jun 5 | Jun 12 | Jun 19 | Jun 26 | Jul 3 | Jul 10 | Jul 17 | Jul 24 | Jul 31 | Aug 7 | Aug 14 | Aug 21 | Aug 28 | Sep 4 | Sep 11 | Sep 18 | Sep 25 | Oct 2 | Oct 9 | Oct 16 | Oct 23 | Oct 30 | Nov 6 | Nov 13 | Nov 20 | Nov 27 | Dec 4 | Dec 11 | Dec 18 | Dec 25 | Jan 1 | Jan 8 | Jan 15 | Jan 22 | Jan 29 | Feb 5 | Feb 12 | Feb 19 | Feb 26 | Mar 5 | Mar 12 | Mar 19 | Mar 26 | Apr 2 | Apr 9 | Apr 16 | Apr 23 | Apr 30 | May 7 | May 14
1 | Consents, ground investigation & procurement |  | 2026-08-02 | 2027-01-18 | 170
1.1 | Ground investigation & borehole programme | Geotech | 2026-08-02 | 2026-09-25 | 55
1.2 | Geotechnical baseline report | Geotech | 2026-09-21 | 2026-10-20 | 30
1.3 | Alignment & tunnel lining design | Designer | 2026-10-01 | 2026-11-29 | 60
1.4 | Planning consent & statutory order | Client | 2026-08-22 | 2027-01-08 | 140
1.5 | TBM specification & tender | Procurement | 2026-11-10 | 2026-12-24 | 45
2 | ◆ TBM contract awarded |  | 2026-12-30 | 2026-12-30 | [22 empty] | ◆
3 | ◆ Consents granted |  | 2027-01-09 | 2027-01-09 | [23 empty] | ◆
4 | Launch shaft & site establishment |  | 2026-12-30 | 2027-07-17 | 200
4.1 | Site establishment & compound | Civils | 2026-12-30 | 2027-02-02 | 35
4.2 | Shaft diaphragm walls | Civils | 2027-02-18 | 2027-04-18 | 60
4.3 | Shaft excavation & base slab | Civils | 2027-04-14 | 2027-06-22 | 70
4.4 | Launch chamber & thrust wall | Civils | 2027-06-13 | 2027-07-17 | 35
4.5 | Segment production run — first 1,000 rings | Casting yard | 2027-04-09 | 2027-08-06 | 120
5 | ◆ Launch shaft ready to receive TBM |  | 2027-07-18 | 2027-07-18 | [51 empty] | ◆
6 | TBM manufacture, delivery & assembly |  | 2026-12-30 | 2027-11-14 | 320
6.1 | TBM detailed design & cutterhead configuration | TBM supplier | 2026-12-30 | 2027-02-27 | 60
6.2 | TBM manufacture | TBM supplier | 2027-02-28 | 2027-07-27 | 150
6.3 | Factory acceptance test | TBM supplier | 2027-07-28 | 2027-08-16 | 20
6.4 | TBM shipping & road transport to site | Logistics | 2027-08-17 | 2027-09-15 | 30
6.5 | TBM lowering & underground assembly | TBM crew | 2027-09-16 | 2027-10-30 | 45
7 | ◆ TBM ready to launch |  | 2027-11-15 | 2027-11-15 | [68 empty] | ◆
8 | Tunnel drive |  | 2027-11-15 | 2028-09-09 | 300
8.1 | TBM launch through the soft eye | TBM crew | 2027-11-15 | 2027-12-04 | 20
8.2 | Learning-curve drive — first 200 m | TBM crew | 2027-12-05 | 2028-01-08 | 35
8.3 | Muck removal & spoil haulage system live | Logistics | 2027-11-15 | 2028-09-09 | 300
8.4 | Segment supply & ring delivery logistics | Casting yard | 2027-11-15 | 2028-09-09 | 300
8.5 | Settlement monitoring & compensation grouting | Instrumentation | 2027-12-05 | 2028-09-09 | 280
8.6 | Sustained drive through mixed ground | TBM crew | 2028-01-09 | 2028-04-27 | 110
8.7 | Hyperbaric intervention & cutter tool change | TBM crew | 2028-04-28 | 2028-05-12 | 15
8.8 | Drive beneath river crossing | TBM crew | 2028-05-13 | 2028-06-26 | 45
8.9 | Final drive to reception shaft | TBM crew | 2028-06-27 | 2028-08-25 | 60
9 | ◆ Breakthrough at reception shaft |  | 2028-08-26 | 2028-08-26 | [108 empty] | ◆
10 | Cross-passages & secondary works |  | 2028-03-24 | 2028-12-08 | 260
10.1 | Cross-passage ground treatment | Ground eng | 2028-03-24 | 2028-05-17 | 55
10.2 | Cross-passage excavation & lining | Mining crew | 2028-05-18 | 2028-08-15 | 90
10.3 | Annulus grouting & ring survey | TBM crew | 2028-07-02 | 2028-08-30 | 60
10.4 | TBM disassembly & removal | TBM crew | 2028-08-26 | 2028-09-29 | 35
10.5 | Secondary lining & invert concrete | Civils | 2028-09-30 | 2028-12-08 | 70
11 | ◆ Tunnel structurally complete |  | 2028-12-09 | 2028-12-09 | [123 empty] | ◆
12 | Fit-out, systems & commissioning |  | 2028-10-30 | 2029-05-12 | 195
12.1 | Walkway, drainage & cable containment | Fit-out | 2028-10-30 | 2028-12-23 | 55
12.2 | Ventilation fans & ductwork installation | Mechanical | 2028-12-09 | 2029-01-27 | 50
12.3 | Fire main, hydrants & suppression system | Mechanical | 2028-12-24 | 2029-02-06 | 45
12.4 | Power distribution & tunnel lighting | Electrical | 2028-12-29 | 2029-02-16 | 50
12.5 | Comms, SCADA & CCTV installation | Systems | 2029-01-28 | 2029-03-08 | 40
12.6 | Hot smoke test & fire drill with emergency services | Commissioning | 2029-03-29 | 2029-04-12 | 15
12.7 | Safety case & regulator approval | Client | 2029-04-13 | 2029-05-12 | 30
13 | ◆ Tunnel handed over for operation |  | 2029-05-13 | 2029-05-13 | [146 empty] | ◆