## Slide 1
Warehouse Setup Project Plan
Free Gantt chart template · gantts.app

## Slide 2
Warehouse Setup Project Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Requirements & network study
Volume & SKU profiling
Throughput & capacity model
Network & location analysis
Capital case & approval
◆ Business case approved
Site selection & lease
Site search & shortlist
Building survey & floor loading
Power & utilities check
Heads of terms & lease negotiation
◆ Lease signed
Layout & racking
Storage strategy & slotting design
Racking layout & permits
Fire & sprinkler design approval
Racking manufacture
Racking installation
◆ Racking complete
WMS selection & integration
WMS requirements & vendor selection
WMS configuration
ERP & carrier integrations
Location & item data migration
WMS user acceptance testing
◆ WMS UAT signed off
MHE & equipment
Forklift & reach truck order
Conveyor & sortation install
Packing benches & print apply
Charging infrastructure
Fit-out & infrastructure
Power, lighting & landlord works
Network & cabling
Wireless survey & access points
Dock levellers & doors
Office, welfare & security
Recruitment & training
Site management hires
Operative recruitment
WMS & process training
Licensed operator certification
Inventory transfer & go-live
Stock cleanse & obsolescence
Transfer wave 1 (fast movers)
Transfer wave 2 (remaining SKUs)
Cycle count & reconciliation
Parallel running
◆ First order shipped
Volume ramp
◆ Full volume
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Requirements & network study |  | 2026-08-02 | 2026-10-10 | 70 | 100%
1.1 | Volume & SKU profiling | Supply chain | 2026-08-02 | 2026-08-31 | 30 | 100%
1.2 | Throughput & capacity model | Supply chain | 2026-08-27 | 2026-09-25 | 30 | 100%
1.3 | Network & location analysis | Consultant | 2026-08-22 | 2026-09-25 | 35 | 100%
1.4 | Capital case & approval | Finance | 2026-09-21 | 2026-10-10 | 20 | 100%
2 | Business case approved |  | 2026-10-11 | 2026-10-11 | — | —
3 | Site selection & lease |  | 2026-10-11 | 2027-01-18 | 100 | 100%
3.1 | Site search & shortlist | Agent | 2026-10-11 | 2026-11-19 | 40 | 100%
3.2 | Building survey & floor loading | Surveyor | 2026-11-10 | 2026-12-04 | 25 | 100%
3.3 | Power & utilities check | M&E consultant | 2026-11-15 | 2026-12-09 | 25 | 100%
3.4 | Heads of terms & lease negotiation | Legal | 2026-12-05 | 2027-01-18 | 45 | 100%
4 | Lease signed |  | 2027-01-19 | 2027-01-19 | — | —
5 | Layout & racking |  | 2026-12-20 | 2027-05-28 | 160 | 40%
5.1 | Storage strategy & slotting design | Consultant | 2026-12-20 | 2027-01-28 | 40 | 80%
5.2 | Racking layout & permits | Racking vendor | 2027-01-24 | 2027-03-04 | 40 | 50%
5.3 | Fire & sprinkler design approval | Consultant | 2027-02-13 | 2027-03-29 | 45 | 20%
5.4 | Racking manufacture | Racking vendor | 2027-03-05 | 2027-04-28 | 55 | 0%
5.5 | Racking installation | Racking vendor | 2027-04-24 | 2027-05-28 | 35 | 0%
6 | Racking complete |  | 2027-05-29 | 2027-05-29 | — | —
7 | WMS selection & integration |  | 2026-11-10 | 2027-06-27 | 230 | 30%
7.1 | WMS requirements & vendor selection | IT & operations | 2026-11-10 | 2027-01-08 | 60 | 100%

## Slide 4
7.2 | WMS configuration | Vendor | 2027-01-14 | 2027-03-29 | 75 | 40%
7.3 | ERP & carrier integrations | IT | 2027-02-13 | 2027-05-03 | 80 | 20%
7.4 | Location & item data migration | IT | 2027-04-09 | 2027-05-23 | 45 | 0%
7.5 | WMS user acceptance testing | Operations | 2027-05-24 | 2027-06-27 | 35 | 0%
8 | WMS UAT signed off |  | 2027-06-28 | 2027-06-28 | — | —
9 | MHE & equipment |  | 2027-01-19 | 2027-06-17 | 150 | 20%
9.1 | Forklift & reach truck order | Procurement | 2027-01-19 | 2027-05-08 | 110 | 30%
9.2 | Conveyor & sortation install | Vendor | 2027-04-29 | 2027-06-07 | 40 | 0%
9.3 | Packing benches & print apply | Vendor | 2027-05-14 | 2027-06-12 | 30 | 0%
9.4 | Charging infrastructure | M&E contractor | 2027-04-09 | 2027-05-13 | 35 | 0%
10 | Fit-out & infrastructure |  | 2027-01-24 | 2027-06-17 | 145 | 20%
10.1 | Power, lighting & landlord works | Landlord | 2027-01-24 | 2027-04-03 | 70 | 40%
10.2 | Network & cabling | IT | 2027-03-30 | 2027-05-03 | 35 | 0%
10.3 | Wireless survey & access points | IT | 2027-05-29 | 2027-06-17 | 20 | 0%
10.4 | Dock levellers & doors | Contractor | 2027-03-20 | 2027-04-28 | 40 | 0%
10.5 | Office, welfare & security | Contractor | 2027-04-09 | 2027-05-28 | 50 | 0%
11 | Recruitment & training |  | 2027-03-10 | 2027-07-17 | 130 | 10%
11.1 | Site management hires | HR | 2027-03-10 | 2027-05-03 | 55 | 40%
11.2 | Operative recruitment | HR | 2027-05-04 | 2027-06-17 | 45 | 0%
11.3 | WMS & process training | Operations | 2027-06-18 | 2027-07-12 | 25 | 0%
11.4 | Licensed operator certification | Training provider | 2027-06-18 | 2027-07-17 | 30 | 0%
12 | Inventory transfer & go-live |  | 2027-06-28 | 2027-10-10 | 105 | 0%
12.1 | Stock cleanse & obsolescence | Supply chain | 2027-05-29 | 2027-06-27 | 30 | 0%
12.2 | Transfer wave 1 (fast movers) | Logistics | 2027-07-13 | 2027-07-27 | 15 | 0%

## Slide 5
12.3 | Transfer wave 2 (remaining SKUs) | Logistics | 2027-07-28 | 2027-08-16 | 20 | 0%
12.4 | Cycle count & reconciliation | Inventory | 2027-08-12 | 2027-08-26 | 15 | 0%
12.5 | Parallel running | Operations | 2027-07-23 | 2027-08-26 | 35 | 0%
13 | First order shipped |  | 2027-07-26 | 2027-07-26 | — | —
13.1 | Volume ramp | Operations | 2027-08-27 | 2027-10-05 | 40 | 0%
14 | Full volume |  | 2027-10-11 | 2027-10-11 | — | —