## Gantt
Warehouse Setup Project Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18
1 | Requirements & network study |  | 2026-08-02 | 2026-10-10 | 70
1.1 | Volume & SKU profiling | Supply chain | 2026-08-02 | 2026-08-31 | 30
1.2 | Throughput & capacity model | Supply chain | 2026-08-27 | 2026-09-25 | 30
1.3 | Network & location analysis | Consultant | 2026-08-22 | 2026-09-25 | 35
1.4 | Capital case & approval | Finance | 2026-09-21 | 2026-10-10 | 20
2 | ◆ Business case approved |  | 2026-10-11 | 2026-10-11 | [11 empty] | ◆
3 | Site selection & lease |  | 2026-10-11 | 2027-01-18 | 100
3.1 | Site search & shortlist | Agent | 2026-10-11 | 2026-11-19 | 40
3.2 | Building survey & floor loading | Surveyor | 2026-11-10 | 2026-12-04 | 25
3.3 | Power & utilities check | M&E consultant | 2026-11-15 | 2026-12-09 | 25
3.4 | Heads of terms & lease negotiation | Legal | 2026-12-05 | 2027-01-18 | 45
4 | ◆ Lease signed |  | 2027-01-19 | 2027-01-19 | [25 empty] | ◆
5 | Layout & racking |  | 2026-12-20 | 2027-05-28 | 160
5.1 | Storage strategy & slotting design | Consultant | 2026-12-20 | 2027-01-28 | 40
5.2 | Racking layout & permits | Racking vendor | 2027-01-24 | 2027-03-04 | 40
5.3 | Fire & sprinkler design approval | Consultant | 2027-02-13 | 2027-03-29 | 45
5.4 | Racking manufacture | Racking vendor | 2027-03-05 | 2027-04-28 | 55
5.5 | Racking installation | Racking vendor | 2027-04-24 | 2027-05-28 | 35
6 | ◆ Racking complete |  | 2027-05-29 | 2027-05-29 | [43 empty] | ◆
7 | WMS selection & integration |  | 2026-11-10 | 2027-06-27 | 230
7.1 | WMS requirements & vendor selection | IT & operations | 2026-11-10 | 2027-01-08 | 60
7.2 | WMS configuration | Vendor | 2027-01-14 | 2027-03-29 | 75
7.3 | ERP & carrier integrations | IT | 2027-02-13 | 2027-05-03 | 80
7.4 | Location & item data migration | IT | 2027-04-09 | 2027-05-23 | 45
7.5 | WMS user acceptance testing | Operations | 2027-05-24 | 2027-06-27 | 35
8 | ◆ WMS UAT signed off |  | 2027-06-28 | 2027-06-28 | [48 empty] | ◆
9 | MHE & equipment |  | 2027-01-19 | 2027-06-17 | 150
9.1 | Forklift & reach truck order | Procurement | 2027-01-19 | 2027-05-08 | 110
9.2 | Conveyor & sortation install | Vendor | 2027-04-29 | 2027-06-07 | 40
9.3 | Packing benches & print apply | Vendor | 2027-05-14 | 2027-06-12 | 30
9.4 | Charging infrastructure | M&E contractor | 2027-04-09 | 2027-05-13 | 35
10 | Fit-out & infrastructure |  | 2027-01-24 | 2027-06-17 | 145
10.1 | Power, lighting & landlord works | Landlord | 2027-01-24 | 2027-04-03 | 70
10.2 | Network & cabling | IT | 2027-03-30 | 2027-05-03 | 35
10.3 | Wireless survey & access points | IT | 2027-05-29 | 2027-06-17 | 20
10.4 | Dock levellers & doors | Contractor | 2027-03-20 | 2027-04-28 | 40
10.5 | Office, welfare & security | Contractor | 2027-04-09 | 2027-05-28 | 50
11 | Recruitment & training |  | 2027-03-10 | 2027-07-17 | 130
11.1 | Site management hires | HR | 2027-03-10 | 2027-05-03 | 55
11.2 | Operative recruitment | HR | 2027-05-04 | 2027-06-17 | 45
11.3 | WMS & process training | Operations | 2027-06-18 | 2027-07-12 | 25
11.4 | Licensed operator certification | Training provider | 2027-06-18 | 2027-07-17 | 30
12 | Inventory transfer & go-live |  | 2027-06-28 | 2027-10-10 | 105
12.1 | Stock cleanse & obsolescence | Supply chain | 2027-05-29 | 2027-06-27 | 30
12.2 | Transfer wave 1 (fast movers) | Logistics | 2027-07-13 | 2027-07-27 | 15
12.3 | Transfer wave 2 (remaining SKUs) | Logistics | 2027-07-28 | 2027-08-16 | 20
12.4 | Cycle count & reconciliation | Inventory | 2027-08-12 | 2027-08-26 | 15
12.5 | Parallel running | Operations | 2027-07-23 | 2027-08-26 | 35
13 | ◆ First order shipped |  | 2027-07-26 | 2027-07-26 | [52 empty] | ◆
13.1 | Volume ramp | Operations | 2027-08-27 | 2027-10-05 | 40
14 | ◆ Full volume |  | 2027-10-11 | 2027-10-11 | [63 empty] | ◆