## Slide 1
Webinar Plan
Free Gantt chart template · gantts.app

## Slide 2
Webinar Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Plan & topic
Define goals & audience
Choose topic, format & date
Confirm speakers & platform
◆ Webinar confirmed
Registration & assets
Build registration & landing page
Create slides & content
Design promo assets
◆ Assets ready
Promotion
Announce & email sequence
Social & partner promotion
Paid promotion (optional)
◆ Registration goal reached
Rehearsal & prep
Speaker prep & content review
Tech check & dry run
Reminder emails
◆ Ready to go live
Live event
Go live & host
Moderate Q&A & engagement
◆ Webinar delivered
Follow-up
Publish recording
Follow-up emails & nurture
Hand leads to sales
Measure & report
◆ Post-webinar review
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Plan & topic |  | 2026-08-02 | 2026-08-11 | 10 | 100%
1.1 | Define goals & audience | Marketing | 2026-08-02 | 2026-08-05 | 4 | 100%
1.2 | Choose topic, format & date | Marketing | 2026-08-05 | 2026-08-08 | 4 | 100%
1.3 | Confirm speakers & platform | Marketing | 2026-08-07 | 2026-08-11 | 5 | 80%
2 | Webinar confirmed |  | 2026-08-12 | 2026-08-12 | , | ,
3 | Registration & assets |  | 2026-08-12 | 2026-08-29 | 18 | 30%
3.1 | Build registration & landing page | Marketing | 2026-08-12 | 2026-08-19 | 8 | 50%
3.2 | Create slides & content | Speaker | 2026-08-14 | 2026-08-27 | 14 | 20%
3.3 | Design promo assets | Designer | 2026-08-16 | 2026-08-21 | 6 | 0%
4 | Assets ready |  | 2026-08-30 | 2026-08-30 | , | ,
5 | Promotion |  | 2026-08-20 | 2026-09-12 | 24 | 0%
5.1 | Announce & email sequence | Marketing | 2026-08-20 | 2026-09-08 | 20 | 0%
5.2 | Social & partner promotion | Marketing | 2026-08-22 | 2026-09-08 | 18 | 0%
5.3 | Paid promotion (optional) | Marketing | 2026-08-26 | 2026-09-04 | 10 | 0%
6 | Registration goal reached |  | 2026-09-13 | 2026-09-13 | , | ,
7 | Rehearsal & prep |  | 2026-09-06 | 2026-09-19 | 14 | 0%
7.1 | Speaker prep & content review | Speaker | 2026-09-06 | 2026-09-12 | 7 | 0%
7.2 | Tech check & dry run | Marketing | 2026-09-13 | 2026-09-16 | 4 | 0%
7.3 | Reminder emails | Marketing | 2026-09-15 | 2026-09-19 | 5 | 0%
8 | Ready to go live |  | 2026-09-20 | 2026-09-20 | , | ,
9 | Live event |  | 2026-09-20 | 2026-09-21 | 2 | 0%

## Slide 4
9.1 | Go live & host | Host | 2026-09-20 | 2026-09-20 | 1 | 0%
9.2 | Moderate Q&A & engagement | Moderator | 2026-09-20 | 2026-09-20 | 1 | 0%
10 | Webinar delivered |  | 2026-09-21 | 2026-09-21 | , | ,
11 | Follow-up |  | 2026-09-21 | 2026-10-02 | 12 | 0%
11.1 | Publish recording | Marketing | 2026-09-21 | 2026-09-23 | 3 | 0%
11.2 | Follow-up emails & nurture | Marketing | 2026-09-22 | 2026-09-29 | 8 | 0%
11.3 | Hand leads to sales | Sales | 2026-09-24 | 2026-09-28 | 5 | 0%
11.4 | Measure & report | Marketing | 2026-09-27 | 2026-10-01 | 5 | 0%
12 | Post-webinar review |  | 2026-10-03 | 2026-10-03 | , | ,