## Gantt
Webinar Plan
Made free at gantts.app, edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5
1 | Plan & topic |  | 2026-08-02 | 2026-08-11 | 10
1.1 | Define goals & audience | Marketing | 2026-08-02 | 2026-08-05 | 4
1.2 | Choose topic, format & date | Marketing | 2026-08-05 | 2026-08-08 | 4
1.3 | Confirm speakers & platform | Marketing | 2026-08-07 | 2026-08-11 | 5
2 | ◆ Webinar confirmed |  | 2026-08-12 | 2026-08-12 |  |  | ◆
3 | Registration & assets |  | 2026-08-12 | 2026-08-29 | 18
3.1 | Build registration & landing page | Marketing | 2026-08-12 | 2026-08-19 | 8
3.2 | Create slides & content | Speaker | 2026-08-14 | 2026-08-27 | 14
3.3 | Design promo assets | Designer | 2026-08-16 | 2026-08-21 | 6
4 | ◆ Assets ready |  | 2026-08-30 | 2026-08-30 | [5 empty] | ◆
5 | Promotion |  | 2026-08-20 | 2026-09-12 | 24
5.1 | Announce & email sequence | Marketing | 2026-08-20 | 2026-09-08 | 20
5.2 | Social & partner promotion | Marketing | 2026-08-22 | 2026-09-08 | 18
5.3 | Paid promotion (optional) | Marketing | 2026-08-26 | 2026-09-04 | 10
6 | ◆ Registration goal reached |  | 2026-09-13 | 2026-09-13 | [7 empty] | ◆
7 | Rehearsal & prep |  | 2026-09-06 | 2026-09-19 | 14
7.1 | Speaker prep & content review | Speaker | 2026-09-06 | 2026-09-12 | 7
7.2 | Tech check & dry run | Marketing | 2026-09-13 | 2026-09-16 | 4
7.3 | Reminder emails | Marketing | 2026-09-15 | 2026-09-19 | 5
8 | ◆ Ready to go live |  | 2026-09-20 | 2026-09-20 | [8 empty] | ◆
9 | Live event |  | 2026-09-20 | 2026-09-21 | 2
9.1 | Go live & host | Host | 2026-09-20 | 2026-09-20 | 1
9.2 | Moderate Q&A & engagement | Moderator | 2026-09-20 | 2026-09-20 | 1
10 | ◆ Webinar delivered |  | 2026-09-21 | 2026-09-21 | [8 empty] | ◆
11 | Follow-up |  | 2026-09-21 | 2026-10-02 | 12
11.1 | Publish recording | Marketing | 2026-09-21 | 2026-09-23 | 3
11.2 | Follow-up emails & nurture | Marketing | 2026-09-22 | 2026-09-29 | 8
11.3 | Hand leads to sales | Sales | 2026-09-24 | 2026-09-28 | 5
11.4 | Measure & report | Marketing | 2026-09-27 | 2026-10-01 | 5
12 | ◆ Post-webinar review |  | 2026-10-03 | 2026-10-03 | [9 empty] | ◆