## Gantt
Website Redesign Project Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17
1 | Discovery |  | 2026-08-02 | 2026-08-31 | 30
1.1 | Stakeholder interviews | Project lead | 2026-08-02 | 2026-08-16 | 15
1.2 | Analytics & Search Console review | SEO | 2026-08-07 | 2026-08-21 | 15
1.3 | Competitor & user research | Strategy | 2026-08-12 | 2026-08-26 | 15
1.4 | Requirements & success metrics | Project lead | 2026-08-22 | 2026-08-31 | 10
2 | ◆ Discovery sign-off |  | 2026-09-01 | 2026-09-01 | [5 empty] | ◆
3 | IA & content audit |  | 2026-09-01 | 2026-10-30 | 60
3.1 | Full URL inventory & crawl | SEO | 2026-09-01 | 2026-09-10 | 10
3.2 | Content audit (keep/merge/retire) | Content lead | 2026-09-11 | 2026-10-10 | 30
3.3 | Sitemap & navigation design | UX | 2026-09-26 | 2026-10-15 | 20
3.4 | Wireframes & key templates | UX | 2026-10-06 | 2026-10-30 | 25
4 | ◆ IA approved |  | 2026-10-31 | 2026-10-31 | [13 empty] | ◆
5 | Design |  | 2026-10-11 | 2026-12-14 | 65
5.1 | Visual direction & moodboards | Design | 2026-10-11 | 2026-10-25 | 15
5.2 | Design system & components | Design | 2026-10-26 | 2026-11-24 | 30
5.3 | Key page designs | Design | 2026-11-10 | 2026-12-09 | 30
5.4 | Responsive & accessibility review | Design | 2026-11-30 | 2026-12-14 | 15
6 | ◆ Design sign-off |  | 2026-12-15 | 2026-12-15 | [20 empty] | ◆
7 | Build |  | 2026-11-30 | 2027-02-27 | 90
7.1 | Environment & CMS setup | Developers | 2026-11-30 | 2026-12-14 | 15
7.2 | Component library build | Developers | 2026-12-15 | 2027-01-18 | 35
7.3 | Template development | Developers | 2026-12-15 | 2027-02-02 | 50
7.4 | Integrations & forms | Developers | 2027-01-24 | 2027-02-17 | 25
7.5 | Search & analytics instrumentation | Developers | 2027-02-08 | 2027-02-22 | 15
8 | ◆ Build feature complete |  | 2027-02-28 | 2027-02-28 | [31 empty] | ◆
9 | Content migration |  | 2026-12-30 | 2027-03-09 | 70
9.1 | Migration mapping sheet | Content lead | 2026-12-30 | 2027-01-18 | 20
9.2 | Content rewriting & optimization | Writers | 2027-01-14 | 2027-02-27 | 45
9.3 | Media & asset migration | Content lead | 2027-02-08 | 2027-03-04 | 25
9.4 | Content load into CMS | Content lead | 2027-02-18 | 2027-03-14 | 25
10 | ◆ Content freeze on old site |  | 2027-03-10 | 2027-03-10 | [32 empty] | ◆
11 | SEO & redirect mapping |  | 2027-01-09 | 2027-03-14 | 65
11.1 | Redirect map: old URL to new URL | SEO | 2027-01-09 | 2027-02-12 | 35
11.2 | Metadata, headings & schema | SEO | 2027-02-13 | 2027-03-09 | 25
11.3 | Redirect rules built & unit tested | Developers | 2027-02-18 | 2027-03-09 | 20
11.4 | Canonicals, robots & XML sitemap | SEO | 2027-03-05 | 2027-03-14 | 10
12 | ◆ Redirect map signed off |  | 2027-03-15 | 2027-03-15 | [33 empty] | ◆
13 | QA |  | 2027-02-23 | 2027-03-29 | 35
13.1 | Cross-browser & device testing | QA | 2027-02-23 | 2027-03-14 | 20
13.2 | Accessibility audit (WCAG) | QA | 2027-02-28 | 2027-03-14 | 15
13.3 | Performance & Core Web Vitals | Developers | 2027-03-05 | 2027-03-19 | 15
13.4 | Redirect crawl on staging | SEO | 2027-03-15 | 2027-03-24 | 10
13.5 | UAT & stakeholder review | Stakeholders | 2027-03-18 | 2027-03-29 | 12
14 | ◆ QA sign-off |  | 2027-03-30 | 2027-03-30 | [35 empty] | ◆
15 | Launch & monitoring |  | 2027-03-30 | 2027-05-11 | 43
16 | ◆ Go / no-go |  | 2027-03-30 | 2027-03-30 | [35 empty] | ◆
16.1 | DNS cutover & launch | Developers | 2027-03-31 | 2027-04-01 | 2
16.2 | Post-launch redirect verification | SEO | 2027-04-02 | 2027-04-08 | 7
16.3 | Submit sitemap & request indexing | SEO | 2027-04-03 | 2027-04-05 | 3
16.4 | Crawl error & 404 monitoring | SEO | 2027-04-02 | 2027-05-11 | 40
16.5 | Rankings & traffic monitoring | SEO | 2027-04-04 | 2027-05-11 | 38
17 | ◆ 30-day post-launch review |  | 2027-05-12 | 2027-05-12 | [41 empty] | ◆