## Gantt
Wedding Planning (12 months)
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5
1 | 12-9 months before |  | 2026-08-02 | 2026-10-30 | 90
1.1 | Set date, budget & guest list | Couple | 2026-08-02 | 2026-08-21 | 20
1.2 | Book venue | Couple | 2026-08-17 | 2026-09-05 | 20
2 | 9-6 months before |  | 2026-10-31 | 2027-01-28 | 90
2.1 | Caterer, photographer & attire | Couple | 2026-10-31 | 2026-12-29 | 60
2.2 | Send invitations | Couple | 2026-12-30 | 2027-01-08 | 10
3 | 3-1 months before |  | 2027-03-30 | 2027-05-28 | 60
3.1 | RSVPs, seating & rehearsal | Couple | 2027-03-30 | 2027-05-18 | 50
4 | ◆ Wedding day |  | 2027-06-28 | 2027-06-28 | [48 empty] | ◆