## Slide 1
Wind Farm Construction Schedule
Free Gantt chart template · gantts.app

## Slide 2
Wind Farm Construction Schedule
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Jun 5
Jun 19
Jul 3
Jul 17
Jul 31
Aug 14
Aug 28
Sep 11
Sep 25
Oct 9
Oct 23
Nov 6
Nov 20
Dec 4
Dec 18
Site assessment & resource
Site selection & land agreements
Met mast / LiDAR install
Wind resource measurement
◆ Resource confirmed
Environmental & permitting
Environmental impact assessment
Noise & avian surveys
◆ Planning consent
Grid connection
Connection application & study
Connection agreement & substation design
Procurement
Turbine supply agreement
Balance of plant & cable orders
Civil works
Access roads & crane pads
Foundations & cure
Cable trenching
Erection & commissioning
Crane mobilization
Tower, nacelle & blade lifts
Electrical termination & testing
◆ First power
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Site assessment & resource |  | 2026-08-02 | 2027-09-05 | 400 | 100%
1.1 | Site selection & land agreements | Development | 2026-08-02 | 2026-10-30 | 90 | 100%
1.2 | Met mast / LiDAR install | Development | 2026-10-21 | 2026-11-19 | 30 | 100%
1.3 | Wind resource measurement | Analyst | 2026-11-20 | 2027-09-05 | 290 | 100%
2 | Resource confirmed |  | 2027-09-06 | 2027-09-06 | — | —
3 | Environmental & permitting |  | 2026-12-30 | 2027-11-14 | 320 | 70%
3.1 | Environmental impact assessment | Consultant | 2026-12-30 | 2027-06-27 | 180 | 100%
3.2 | Noise & avian surveys | Consultant | 2027-02-18 | 2027-07-17 | 150 | 90%
4 | Planning consent |  | 2027-11-15 | 2027-11-15 | — | —
5 | Grid connection |  | 2027-01-29 | 2028-02-12 | 380 | 50%
5.1 | Connection application & study | Development | 2027-01-29 | 2027-09-05 | 220 | 80%
5.2 | Connection agreement & substation design | Engineering | 2027-09-06 | 2028-02-12 | 160 | 30%
6 | Procurement |  | 2027-11-15 | 2028-06-01 | 200 | 20%
6.1 | Turbine supply agreement | Procurement | 2027-11-15 | 2028-02-12 | 90 | 40%
6.2 | Balance of plant & cable orders | Procurement | 2028-01-04 | 2028-06-01 | 150 | 10%
7 | Civil works |  | 2028-03-24 | 2028-08-20 | 150 | 0%
7.1 | Access roads & crane pads | Civil | 2028-03-24 | 2028-05-22 | 60 | 0%
7.2 | Foundations & cure | Civil | 2028-05-03 | 2028-07-31 | 90 | 0%
7.3 | Cable trenching | Electrical | 2028-05-23 | 2028-07-31 | 70 | 0%
8 | Erection & commissioning |  | 2028-08-11 | 2028-12-18 | 130 | 0%
8.1 | Crane mobilization | Erection | 2028-08-11 | 2028-08-30 | 20 | 0%

## Slide 4
8.2 | Tower, nacelle & blade lifts | Erection | 2028-08-29 | 2028-11-01 | 65 | 0%
8.3 | Electrical termination & testing | Commissioning | 2028-10-25 | 2028-12-03 | 40 | 0%
9 | First power |  | 2028-12-19 | 2028-12-19 | — | —